## Budget
OrganizationOrCountry | Provider | Foundational Element | Milestone + Milestone definition | FundingSource | Budget | Amount to be reprogrammed or moved to 2025 | Milestone Due Date in 2024 (as per PO) | Revised due date (where applicable) | Status (Complete, On track, Delayed) as of September 19, 2024 | Status update (include any reasons for deviations from plan) | Start date | End date | Justification/documentation for completion (+ date submitted by the Provider)
Africa CDC | LMH | Continental coordination mechanisms for community health | Milestone 1: Joint country support plan undertaken in Liberia Definition: Joint country support plan Liberia report | BIRCH | 69319 |  | 2024-08-31 | 2024-12-31 | Delayed | Planned for last quarter of 2024 by Africa CDC (November 4 - 8) Africa CDC has initiated discussions with MOH Liberia re this JCSP; Africa CDC has received the TOR and budgets. Africa CDC are awaiting the official request from MOH this week. | 2024-11-04 | 2024-11-08
Africa CDC | LMH | Continental coordination mechanisms for community health | Milestone 2: A technical officer recruited and deployed Definition: A letter from Africa CDC confirming that the staff has been employed and deployed | BIRCH | 104875 |  | 2024-07-31 | 2024-12-31 | Delayed | The recruitment in Africa CDC has not yet been approved by the DG. AFF is having discussions with Africa CDC on the way forward for this recruitment
Africa CDC | LMH | Continental coordination mechanisms for community health | Milestone 3: Joint country support plan undertaken in Uganda Definition: Joint country support plan Uganda report | BIRCH | 69319 |  | 2024-09-30 | 2024-11-30 | Delayed | Planned for last quarter of 2024 by Africa CDC (October 16 - 18) | 2024-10-16 | 2024-10-18
Africa CDC | LMH | Continental coordination mechanisms for community health | Milestone 4: Consultant to support the development of continental guidance on Integrated Community Health Services Delivery Definition: CHWs SOPs/Guidelines | BIRCH | 57500 |  | 2024-09-01 | 2024-12-31 | Delayed | SoPs 2nd draft under review by Africa CDC
Africa CDC | LMH | Continental coordination mechanisms for community health | Milestone 5: Joint country support plan undertaken in Malawi Definition: Joint country support plan Malawi report | BIRCH | 69319 |  | 2024-10-31 | 2024-10-31 | On track | Planned for last quarter of 2024 by Africa CDC (October 14 - 18) | 2024-10-14 | 2024-10-18
Africa CDC | LMH | Continental coordination mechanisms for community health | Milestone 6: Hold a member state convening for cross-learning and experience-sharing on key thematic topics for community health, including sustainable financing, integration, climate change and other topics TBD Definition: A report of the learning event | BIRCH | 78126 |  | 2024-12-15 | 2024-12-15 | On track | Africa CDC and AFF are planning a side event on increased domestic financing for community health at the 3rd annual International Conference on Public Health in Africa scheduled on November 26 - 28, 2024
Africa CDC | LMH | Continental coordination mechanisms for community health | Milestone 7: Community health scorecard developed, validated and operationalised for the continent Definition: The Scorecard | BIRCH | 69000 |  | 2024-12-30 | 2025-01-31 | Delayed | This is anticipated to extend to 2025 because Africa CDC Director General proposed a different approach, starting with a survey that captures and serves as the baseline of the the current status of community health and will inform the targets that will be tracked via the scorecard. The survey will be launched in mid-September (tentaively) and the report will be dessiminated in November during CPHIA. The Africa CDC is concurrently developing an indicator framework for the scorecard.
BIRCH HQ | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone 1: AFF-ACDC management support (JSCP, scorecard etc.) Definition: Report from the cross-learning and experience-sharing session on progress and system change, held during CPHIA 2024 Presentations and recommendations from ACDC events | BIRCH | 129839 |  | 2024-12-31 | 2024-12-31 | On track | AFF continues to provide technical support to Africa CDC in the implementation of the Africa CDC workplan activities
BIRCH HQ | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone 2: Stakeholder working sessions with Global Fund Definition: Geneva in-person working session minutes and reports | BIRCH | 32035 |  | 2024-05-31 | 2024-05-31 | Complete
BIRCH HQ | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone 3: Project BIRCH design, mechanisms, and structure introduced to all BIRCH countries including relevant stakeholders such as MOH, Global Fund Country Teams, and other country or regional actors. Mechanism and tools established for engaging MOH, implementing partners and in-country stakeholders. Definition: Communications sent to countries informing countries of their BIRCH expansion and strategic initiative envelope and eligibility Minutes of socialization/launch calls held with MOH, Global Fund Country Teams and BIRCH TA providers Prioritization and workplanning guidance | BIRCH | 361788 |  | 2024-12-31 | 2024-12-31 | On track
BIRCH HQ | LMH | Quarterly monitoring reports on implementation of community health investments (based on Detailed implementation plans) including identification of programmatic and absorption bottlenecks, problem solving and resolution in targeted regions | Milestone 1: Mechanism and tools for Contracting, monitoring, and reporting established. This will include the financial and programmatic reporting tools; IPs quarterly reports; LMH reports to the Global Fund Definition: BIRCH Quarterly Reporting Template for IPs developed Quarterly contracting and financial reporting of BIRCH progress (Contributions to quarterly reports to Global Fund) | BIRCH | 231887 |  | 2024-12-31 | 2024-12-31 | On track
BIRCH HQ | LMH | Quarterly monitoring reports on implementation of community health investments (based on Detailed implementation plans) including identification of programmatic and absorption bottlenecks, problem solving and resolution in targeted regions | Milestone 2: Presentations and recommendations from relevant fora where Project BIRCH was represented (ad hoc) Definition: BIRCH Communication plans, tools and templates design | BIRCH | 4025 |  | 2024-12-31 | 2024-12-31 | On track
BIRCH HQ | LMH | Quarterly monitoring reports on implementation of community health investments (based on Detailed implementation plans) including identification of programmatic and absorption bottlenecks, problem solving and resolution in targeted regions | Milestone 3: Mechanism and tools for monitoring, evaluation, reporting, and learning established. This will include the MERL framework; financial and programmatic reporting tools; IPs monthly and quarterly reports; LMH reports to the Global Fund [Quarterly reports to the Global Fund (Q1, Q2 & Q3) + final report] Definition: Country dashboard/implementation tracker This will include the MERL framework; financial and programmatic reporting tools; IPs monthly and quarterly reports; LMH reports to the Global Fund [Quarterly reports to the Global Fund (Q1, Q2 & Q3) + final report] | BIRCH | 508509 |  | 2024-12-31 | 2024-12-31 | On track
BIRCH HQ | LMH | Quarterly monitoring reports on implementation of community health investments (based on Detailed implementation plans) including identification of programmatic and absorption bottlenecks, problem solving and resolution in targeted regions | Milestone 4: TA reports/country implementation reports and in-country mission reports. Definition: BIRCH guidance, tools and templates TA reports/country implementation reports and in-country mission reports. | BIRCH | 45920 |  | 2024-09-30 | 2024-09-30 | On track
BIRCH HQ | LMH | Integrated HRH/CHW Strategic Plan | Milestone 1: Country inventories completed and submitted to the Global Fund Definition: Approved country inventories | BIRCH | 275028 |  | 2024-06-30 | 2024-10-31 | Delayed | Delayed in Nigeria and Tanzania
BIRCH HQ | LMH | Integrated HRH/CHW Strategic Plan | Milestone 2: Work plans and budgets developed and finalized as part of contracting process Definition: Approved workplans + budgets | BIRCH | 80364 |  | 2024-06-30 | 2024-12-31 | Delayed | Delayed in Nigeria and Tanzania
BIRCH HQ | LMH | Integrated HRH/CHW Strategic Plan | Milestone 3: Convening and stakeholders engagement reports Definition: Convening and stakeholders engagement reports | BIRCH | 229759 |  | 2024-12-31 | 2024-12-31 | On track
Burkina Faso | LMH | Amélioration ciblée de la qualité des soins et de la qualité dans les domaines prioritaires d'investissement des ASC | Milestone 1: ACQ 3 : Le rapport d’atelier d’élaboration et de validation des modalités de mise en œuvre des primes basées sur la performance des ASBC est disponible d’ici fin septembre 2024 Definition: TDRS de l'activité, le document sur les modalités potant primes de performances des ASBC (The workshop report on the development and validation of the implementation modalities for performance-based incentives for ASBCs will be available by the end of September 2024 Definition: Terms of Reference (TOR) for the activity and the document on the modalities concerning performance-based incentives for Community Health Workers (ASBCs)) | BIRCH | 22939.4 |  | 2024-08-31 | 2024-08-31 | Complete |  | 2024-02-01 | 2024-06-01 | TOR of the workshop; Report of the workshop; Document on the modalities concerning performance-based incentives for Community Health Workers (ASBCs)
Burkina Faso | LMH | Amélioration ciblée de la qualité des soins et de la qualité dans les domaines prioritaires d'investissement des ASC | Milestone 2: ACQ 4 : Le rapport d’atelier d’élaboration et de validation et des directives de mise en œuvre de la PCIME chez les ASBC à moins de 5 km est disponible d’ici fin Juin 2024 Definition: TDRS de l'activité , le document d'orientation validé sur la PCIME a moins de 5 km (The workshop report on the development and validation of the implementation guidelines for IMCI (Integrated Management of Childhood Illnesses) by CHWs (Community Health Workers) within a 5 km radius will be available by the end of June 2024. Definition: Terms of Reference for the activity, and the validated guidance document on IMCI within 5 km) | BIRCH | 17238.76 |  | 2024-06-30 | 2024-06-30 | Complete |  | 2024-05-01 | 2024-05-31 | ToR of the activity; Report of the activity; Validated guidance document on IMCI within 5 km
Burkina Faso | LMH | Amélioration ciblée de la qualité des soins et de la qualité dans les domaines prioritaires d'investissement des ASC | Milestone 3: ACQ 7 : Le rapport de supervision annuelle conjointe des 12 districts pilotes Mheath par les directions techniques nationales et les partenaires est disponible un mois après la fin de l’année Definition: TDRS de l'activité , le rapport final de supervision annuelle conjointe des 12 Districts pilotes de Mhealth (The joint annual supervision report of the 12 pilot mHealth districts by national technical departments and partners will be available one month after the end of the year. Definition: Terms of Reference for the activity, and the final joint annual supervision report of the 12 pilot mHealth districts) | BIRCH | 2607.22 |  | 2024-12-31 | 2024-12-31 | On track | Tools are already in place, activities already done last year, so ToR and too will be update for this purpuse
Burkina Faso | LMH | Amélioration ciblée de la qualité des soins et de la qualité dans les domaines prioritaires d'investissement des ASC | Milestone 4: ACQ 8 : Les rapports de revues trimestrielles de performances des ASBC des sites d’intervention LG sont disponibles 1 mois après chaque trimestre ( 2024, 2025, 2026) Definition: TDRs de rencontres , les rapport de revue de performances trimestrielles (The quarterly performance review reports of ASBC from LG intervention sites will be available one month after each quarter (2024, 2025, 2026). Definition: Terms of Reference for the meetings, and the quarterly performance review reports.) | BIRCH | 47039.52 |  | 2024-10-31 | 2024-10-31 | On track | Quaterly milestone. Q1 performance review done; Q2 performance review ongoing |  |  | Q1 ToR;Q1 performance review report;
Burkina Faso | LMH | Amélioration ciblée de la qualité des soins et de la qualité dans les domaines prioritaires d'investissement des ASC | Milestone 5: ACQ 9 : Le rapport de l’atelier de lancement de la phase 2 de BIRCH /SI est disponible d’ici fin Juin 2024 Definition: TDrs de l'activité , rapport de l'atelier de lancement de BIRCH 2+IS (The report from the launch workshop of the second phase of BIRCH/SI will be available by the end of June 2024. Definition: Terms of Reference for the activity, and the report from the BIRCH 2+IS launch workshop.) | BIRCH | 11393.36 |  | 2024-06-30 | 2024-06-30 | Complete |  | 2024-05-01 | 2024-06-01 | ToR workshop; Report of the launch workshop
Burkina Faso | LMH | Amélioration ciblée de la qualité des soins et de la qualité dans les domaines prioritaires d'investissement des ASC | Milestone 6: ACQ 10 : Les rapports des rencontres bimestrielles des membres du comité technique de BIRCH 2 sont disponibles tous les deux mois (2024, 2025 ,2026) Definition: TDRS des rencontres , rapports des rencotres bimestrielles (The reports from the bi-monthly meetings of the BIRCH 2 technical committee members will be available every two months (2024, 2025, 2026). Definition: Terms of Reference for the meetings, and reports from the bi-monthly meetings.) | BIRCH | 8078.07 |  | 2024-11-30 | 2024-11-30 | On track | BIRCH technical committed not in place yet. 3 sessions initially planned but only 1 or 2 sessions possible in 2024 giving delay in the committe setting. Few budget could be save
Burkina Faso | LMH | Amélioration ciblée de la qualité des soins et de la qualité dans les domaines prioritaires d'investissement des ASC | Milestone 7: ACQ 11 : Le rapport de l’atelier bilan & Planification du projet BIRCH est disponible en fin de chaque année 2024, 2025 Definition: TDRS de l'activité, rapport d'activité de l'activité bilan intégrant les orientations pour l'année suivante (The report of the BIRCH project review and planning workshop is available at the end of each year (2024, 2025). Definition: Terms of Reference for the activity, report of the review activity, including directions for the following year.) | BIRCH | 7459.32 |  | 2024-10-31 | 2024-12-31 | On track | ToR/tools to be developped. To start in october and end in december 2024
Burkina Faso | LMH | Rapports de suivi trimestriels sur la mise en œuvre des investissements dans la santé communautaire (sur la base de plans de mise en œuvre détaillés), y compris l'identification des goulots d'étranglement en matière de programmation et de capacité d'absorption, la résolution des problèmes et leur résolution dans les régions ciblées. | Milestone 1: RST 1 : Les rapports de sorties de supervisons semestrielles pour la collecte des données sur les investissements du fonds mondial en santé communautaire sont disponibles un mois après la supervision (2024, 2025, 2026) Definition: TDRS de mission terrain, fiches de collecte de données renseignées , rapports de sorties de supervision (The reports from the semi-annual supervision visits for data collection on Global Fund investments in community health will be available one month after the supervision (2024, 2025, 2026). Definition: Terms of Reference for field missions, completed data collection forms, and supervision visit reports.) | BIRCH | 8242.3 |  | 2024-07-31 | 2024-12-31 | Delayed | GC7& C19RM implementation activities have not fully started, Secondary recipients recruited in Q2 and no tangible activities implemented. [EF]
Burkina Faso | LMH | Rapports de suivi trimestriels sur la mise en œuvre des investissements dans la santé communautaire (sur la base de plans de mise en œuvre détaillés), y compris l'identification des goulots d'étranglement en matière de programmation et de capacité d'absorption, la résolution des problèmes et leur résolution dans les régions ciblées. | Milestone 2: RST 2 : Les rapports des réunions trimestrielles d’examen et de retour d’informations avec les parties prenantes sont disponibles un mois après le trimestre Definition: TDRS de l'activité , rapport de l'activité intgrant les recommandatons formulées | BIRCH | 3652.88 |  | 2024-09-30 | 2024-12-31 | Delayed | Report will be developed as a result of the supervision and/or quarterly review meeting of the GF CH investments. PR did not have budget to organized these quaterly review meetings. LG to still develop a report by en of October 2024 based on discussion qith the stakeholders highlithting challenges/bottlenecks on GC7/C19RM implementation and action plan (even if the supervision did not happen) [Desire: to have reports on implementation by end of Sep and end of Dec]
Burkina Faso | LMH | Rapports de suivi trimestriels sur la mise en œuvre des investissements dans la santé communautaire (sur la base de plans de mise en œuvre détaillés), y compris l'identification des goulots d'étranglement en matière de programmation et de capacité d'absorption, la résolution des problèmes et leur résolution dans les régions ciblées. | Milestone 3: RST 3 : Un plan d’action trimestriel détaillé de mise en œuvre et de suivi des recommandations issues des rencontres trimestrielles est disponible 1 mois après le trimestre Definition: TDRS de l'activité , le plan trimestriel detaillé ,rapport d'avancement de la mise en oeuvre des activités intégrant les recommandations | BIRCH | 1122 |  | 2024-07-31 | 2024-12-31 | Delayed | Linked to milestones 1 & 2. To be developped after supervision and/or quaterly review of GF CH investments [EF]
Burkina Faso | LMH | Rapports de suivi trimestriels sur la mise en œuvre des investissements dans la santé communautaire (sur la base de plans de mise en œuvre détaillés), y compris l'identification des goulots d'étranglement en matière de programmation et de capacité d'absorption, la résolution des problèmes et leur résolution dans les régions ciblées. | Milestone 4: RST 4: Le rapport annuel de revue de performance de la mise en œuvre de stratégie nationale de santé communautaire est disponible en fin janvier de chaque année ( 2024, 2025, 2026) Definition: TDRs de l'activité, rapport annuel de revue de l'activité de revue de performance | BIRCH | 7359.22 |  | 2024-11-30 | 2024-11-30 | On track
Burkina Faso | LMH | Rapports de suivi trimestriels sur la mise en œuvre des investissements dans la santé communautaire (sur la base de plans de mise en œuvre détaillés), y compris l'identification des goulots d'étranglement en matière de programmation et de capacité d'absorption, la résolution des problèmes et leur résolution dans les régions ciblées. | Milestone 5: RST 5: Le rapport des rencontres de la task force régionale en santé communautaire organisées dans les régions sanitaires du plateau central et du cendre sud est disponible en fin T4 de chaque année Definition: TDRS , rapports des rencontres de chaque rencontre de la task force | BIRCH | 7641.92 |  | 2024-10-31 | 2024-10-31 | On track | [Explore the BIRCH HQ budget for theTWGs to support the quarterly review meetings] --->comments to be transfered to row 18+++
Burkina Faso | LMH | Répertoire national fonctionnel et géoréférencé des ASC hébergé dans un registre | Milestone 1: LMGR 1 : Le rapport d’analyse de la cartographie des ASBC est disponible d’ici avril 2024 Definition: TDRS, rapport d'analyse de la cartographie des ASBC | BIRCH | 13803.02 |  | 2024-04-30 | 2024-04-30 | Complete |  | 2024-02-01 | 2024-05-01 | ToR of the ASBC mapping ; Final report of the ASBC mapping
Burkina Faso | LMH | Répertoire national fonctionnel et géoréférencé des ASC hébergé dans un registre | Milestone 2: LMGR 2 : Le design de la géolocalisation/masterlist des ASBC est disponible d’ici fin juin 2024 Definition: TDRS de l'activité , rapport de l'activité d'amendement et de valiadtion, le design du masterlist | BIRCH | 51910.54 |  | 2024-07-31 | 2024-10-31 | Delayed | In 2024, the focus was sitiational analysis and CHML design validation. The next steps will be adressed in 2025. The milestone activities ' implementation has started: in August, Living has visited Mali in for experiences sharing on CH master list. A concept note for the CH ML is under development as well as a draft of the master list design [IF]. CFP is supporting the process [delayed due to wrokplanning process; sufficient internal capacity] [Peter: do theyhave sufficient technical capacity] [2025 activity]
Burkina Faso | LMH | Surveillance communautaire basée sur les événements (prestation à définir avec le ministère de la santé et les prestataires d'assistance technique SONAR+BIRCH dans les pays concernés) | Milestone 1: SCBE 1 : Le rapport d'évaluation annuelle de la maturité du système de SCBE validé est disponible et partagé avec les principales parties prenantes d’ici fin juin 2024 Definition: TDRs de l'activité, rapport d'évaluation de la maturité du systèle de santé communautaire | BIRCH | 12738 |  | 2024-09-30 | 2024-09-30 | On track | A workshop planned next week
Burkina Faso | LMH | Cartographie annuelle des investissements dans la santé communautaire par rapport à la stratégie nationale de santé communautaire (y compris l'intégration de la cartographie des investissements dans la santé communautaire dans les processus nationaux de cartographie des ressources et de suivi des dépenses). | Milestone 1: CISC 1 : Une note conceptuelle pour la cartographie annuelle décentralisée des investissements dans la santé communautaire validée est disponible d’ici fin Juin 2024 Definition: Une note conceptuelle de la cartographie décentralisée, outil de cartographie décentralisé mis à jour pour prendre en compte la santé communautaire | SI | 4058.78 |  | 2024-07-31 | 2024-09-30 | Delayed | Data collection tool was revised and data colelction has started. Concept note under developement retrospectively. [IF]. CFP is supporting the concept note development [risk of duplication --> current support by CHAI, UNICEF that could potentially overlaps with BIRCH scope]
Burkina Faso | LMH | Cartographie annuelle des investissements dans la santé communautaire par rapport à la stratégie nationale de santé communautaire (y compris l'intégration de la cartographie des investissements dans la santé communautaire dans les processus nationaux de cartographie des ressources et de suivi des dépenses). | Milestone 2: CISC 2 : Le rapport de la cartographie des intervenants en santé communautaire (Bailleurs, ONG, ASSOCIATIONS etc) est disponible d’ici fin juin 2024 Definition: TDR recrutement de consultants + contrat de consultance , rapport de cartographie des intervenants | SI | 7957.18 |  | 2024-08-31 | 2024-12-31 | Delayed | [IF]. Concept note under developement (for resources mapping & stakeholders maping).
Burkina Faso | LMH | Cartographie annuelle des investissements dans la santé communautaire par rapport à la stratégie nationale de santé communautaire (y compris l'intégration de la cartographie des investissements dans la santé communautaire dans les processus nationaux de cartographie des ressources et de suivi des dépenses). | Milestone 3: CISC 3 : Le rapport compilé des ateliers régionaux de validation des données collectées au niveau décentralisé pour alimenter le rapport global de cartographie des ressources en santé disponible Definition: Rapport complié de la cartographie décentralisée des ressources en santé communautaire des différentes régions | SI | 22040.48 |  | 2024-11-30 | 2024-11-30 | On track
Burkina Faso | LMH | Des plans opérationnels détaillés et coûtés pour la mise en œuvre de la stratégie nationale de santé communautaire, couvrant au moins les activités de CHW dans les subventions de fonds mondiaux pour faciliter la mise en œuvre des investissements CHW financés par les subventions de fonds mondiaux. | Milestone 1: PAO.1 : Un plan opérationnel détaillé et budgétisé pour la mise en œuvre de la stratégie nationale santé communautaire est disponible en fin T1 de chaque année Definition: les TDRS de l'activité, raport de l'activité ,le document du plan détaillé operationnel et budgetisé | SI | 7158.8 |  | 2024-06-30 | 2024-12-31 | On track | In Q2 2024, the CH strategy operational plan for the remaining 6 months was developed, awaiting for supporting documentation. In Q4 2024, the milestone will be fully completed with the development of the CH strategy perational plan for 2025
Burkina Faso | LMH | Des plans opérationnels détaillés et coûtés pour la mise en œuvre de la stratégie nationale de santé communautaire, couvrant au moins les activités de CHW dans les subventions de fonds mondiaux pour faciliter la mise en œuvre des investissements CHW financés par les subventions de fonds mondiaux. | Milestone 2: PAO.2 : Le rapport de la mise en place du mécanisme de coordination et de suivi de la mise en œuvre de la stratégie santé communautaire est disponible d’ici fin août 2024 Definition: TDRs , courriers d'invitation, rapport de l'activité, le document synthèse du mecanisme de coordination et du suivi de la stratégie de la stratégie santé communautaire | SI | 4874.32 |  | 2024-08-31 | 2024-10-31 | Delayed | Need more discussions with LG about the relevance of this milestone [ythere is a taskforce already in place] [Ann: avoid creating parallel structures; is there a TWG in place] [Peter: was this requested for by the MOH or others?]
Burkina Faso | LMH | Évaluation annuelle de la maturité des systèmes des ASC | Miestone 1: EAM 1 : L’outil d’évaluation de la maturité du système de santé communautaire est adopté au niveau national (institutionnalisé) d’ici fin juin 2024 Definition: TDrs de l'activité ,rapport de l'activité d'examen des outils existants, le rapport de l'atelier sur le système de mturité de la santé communautaire | SI | 20534.8 |  | 2024-07-31 | 2024-10-31 | Delayed | In 2023, AFF & Unicef have counducted CH programme assessment with differents tools. The country wanted to analyse the 2 tools and decide how to agree with only one that will be adopted. Workshop planification on going (mid september 2024). [UNICEF has planned a performance evaluation?]
Burkina Faso | LMH | Évaluation annuelle de la maturité des systèmes des ASC | Milestone 2: EAM 2 : Le rapport d’atelier de formation des acteurs sur l’utilisation de l’outil d’analyse national du système de maturité de la santé communautaire est disponible d’ici fin Août 2024 Definition: TDRs, rapport de l'activité de formation des actuers sur l'utilisation du nouveau outil | SI | 12728.87 |  | 2024-08-31 | 2024-10-31 | Delayed | [MA workshop was planeed for 2025; CFP pushing to see how to combine with these milestones] [Peter: translation into French; sharing with MOH for buy-in and roll out] [MA tool to be shared with translators]
Burkina Faso | LMH | Plan de financement durable à long terme (8-10 ans) et plan de mobilisation des ressources pour la santé communautaire / les agents de santé communautaire | Milestone 1: PFD 1 : Le projet de plan de financement durable et du plan de mobilisation des ressources est amendé d’ici fin septembre 2024 Definition: TDR recrutement consultant , contrat consultant, draft de plan de financement et de mobilisation des ressources | SI | 58015.87 |  | 2024-09-30 | 2024-11-30 | On track | The health financing specialist joined Living Goods team last week. Will stard developing the concept note and discuss with the MoH for alignment (MoH is more in the process of developing a health financing plan rather than CH financing plan, nutrition financing plan, etc) [need new due dates for the draft]
Burkina Faso | LMH | Plan de financement durable à long terme (8-10 ans) et plan de mobilisation des ressources pour la santé communautaire / les agents de santé communautaire | Milestone 2: PFD 2 : Le plan de financement durable et le plan de mobilisation des ressources sont validés d’ici fin Décembre 2024 Definition: TDRs , version validée du plan de finanement et de mobiliation de ressources | SI | 4989.38 |  | 2024-12-31 | 2024-12-31 | On track
Burkina Faso | LMH | Stratégie nationale de santé communautaire actualisée et chiffrée | Milestone 1: SNSC 1 : Le document de stratégie nationale santé communautaire 2024 -2028 et documents annexes validés d’ici fin juin 2024 Definition: Stratégie nationale validée 2024-2028, plan de suivi evaluation, plan de communication, plan triennal glissant | SI | 27852.88 |  | 2024-06-30 | 2024-06-30 | Complete |  | 2024-01-01 | 2024-06-30 | Validated national strategy 2024-2028 toolkit (including a Monitoring and evaluation plan; Communication plan; rolling three-year plan).
Burkina Faso | LMH | Stratégie nationale de santé communautaire actualisée et chiffrée | Milestone 2: SNSC 2 : Le rapport des 3 rencontres de diffusion de la stratégie nationale santé communautaire et ses documents annexes est disponible d’ici fin décembre 2024 Definition: TDRS(3), Rapports de l'activité (3) intégrat les recommandations | SI | 25993.44 |  | 2024-12-31 | 2024-12-31 | On track
Burkina Faso | LMH | Stratégie nationale de santé communautaire actualisée et chiffrée | Milestone 3: SNSC 3 : Le document de capitalisation du processus d’écriture de la stratégie nationale de santé communautaire 2024-2028 est disponible d’ici fin juillet 2024 Definition: Contrat de consultant, TDRS de l'activité de capitalisation, le document de capitalistion du processus d'ecriture de la stratégie santé communautaire | SI | 15695.9 |  | 2024-07-31 | 2024-12-31 | Delayed | LG. CFP Can support with concept note development [documenting of lessons learned from the strategy development process] [October is too soon as the new due date]
Burkina Faso | LMH | Stratégie nationale de santé communautaire actualisée et chiffrée | Milestone 4: SNSC 4 : Un dossier d’investissement sur la santé communautaire 2024-2028 est disponible d’ici fin juin 2025 Definition: TDRs de recrutement du consultant+ Contrat de consultance | SI | 6967.4 |  | 2024-12-31 | 2024-12-31 | On track | Need more clarification. Internal discussions at MoH about the relevance of investments cases [could potentially be changed to updating of PHC strategy]
Cameroon | LMH | Annual assessment of CHW systems maturity | Milestone 1: Maturity assessment of CHW system leveraging LMH model is completed Definition: Assessment report (2024, 2025) | BIRCH | 20146 |  | 2024-12-15 | 2024-12-15 | On track
Cameroon | LMH | Annual assessment of CHW systems maturity |  | BIRCH | 21026 |  | 2025-12-15 | 2025-12-15 | On track
Cameroon | LMH | Annual mapping of investments in community health against the national community health strategy (including integration of community health investment mapping into national Resource Mapping and Expenditure Tracking processes) | Milestone 1: Gap analysis developed against CHW strategy - to help inform updates to new strategy Definition: Gap analysis report with recommendations for CH financing to be included in CHW strategy | BIRCH | 9416 |  | 2025-09-30 | 2025-09-30 | On track
Cameroon | LMH | Annual mapping of investments in community health against the national community health strategy (including integration of community health investment mapping into national Resource Mapping and Expenditure Tracking processes) | Milestone 2: Mapping of community health financial resources completed Definition: Report of CH financial resource mapping | BIRCH | 4160 |  | 2025-01-11 | 2025-01-11 | On track
Cameroon | LMH | Annual mapping of investments in community health against the national community health strategy (including integration of community health investment mapping into national Resource Mapping and Expenditure Tracking processes) |  | BIRCH | 5256 |  | 2025-09-30 | 2025-09-30 | On track
Cameroon | LMH | Annual mapping of investments in community health against the national community health strategy (including integration of community health investment mapping into national Resource Mapping and Expenditure Tracking processes) | Milestone 3: RMET tool developed to capture and organize CHW investments across partners Definition: RMET tool | BIRCH | 9416 |  | 2025-05-05 | 2025-05-05 | On track
Cameroon | LMH | Capacity assessment of relevant MOH directorates (CH/HRH) and tailored capacity building plan developed and implemented | Milestone 1: Management and implementation capacity assessment is conducted with emphasis on district-level capacity Definition: Capacity Assessment tool; Report on management and implementation capacity gaps | BIRCH | 28215 |  | 2024-12-21 | 2024-12-21 | On track
Cameroon | LMH | Capacity assessment of relevant MOH directorates (CH/HRH) and tailored capacity building plan developed and implemented | Milestone 2: Model District Conceptual framework is drafted to facilitate and measure effective decentralization of management of PHC (including CHW program and supervisions) Definition: Finalized model District conceptual framework document | BIRCH | 104639 |  | 2024-12-15 | 2024-12-15 | On track
Cameroon | LMH | Capacity assessment of relevant MOH directorates (CH/HRH) and tailored capacity building plan developed and implemented | Milestone 3: Recommendations developed on implementation of the conceptual framework Definition: Validation Workshop report for District framework and capacity improvement plan | BIRCH | 9416 |  | 2025-03-30 | 2025-03-30 | On track
Cameroon | LMH | Updated and costed national community health strategy | Milestone 1: Evidence generated and recommendations developed to inform the next costed national CHW strategy and subsequent operational planning, including resource mobilization plan and intervention design Definition: Report of compiled recommendations developed from all assessments done under BIRCH to inform evidence-based strategies and interventions in the updated CHW strategy | BIRCH | 19099 |  | 2025-12-31 | 2025-12-31 | On track
Cameroon | LMH | Updated and costed national community health strategy | Milestone 2: Midterm community health program review is conducted, including establishment of steering committees, development of SOPs and tools and data collection Definition: Mid-term review report Steering Committee ToRs SOPs and data collection tools" | BIRCH | 69210 |  | 2025-01-31 | 2025-01-31 | On track
Cote d'Ivoire | LMH | Amélioration ciblée de la qualité des soins et de la qualité dans les domaines prioritaires d'investissement des ASC | Milestone 1: Développement d’une application de digitalisation des outils primaires des Agents de Santé Communautaire (ASC) afin d’améliorer la qualité des données communautaires Definition: Disponibilité d'un lien d'accès à l'application CHT opérationnelle (2024) Rapports des activité de la phase pilote (2025) | BIRCH | 310714.85 |  | 2024-12-31 | 2024-12-31 | On track | Discussions ongoind with the Conultant; Process will be lauched soon. The amount will be spent by due date [clarify the investment areas given the heavy investment]
Cote d'Ivoire | LMH | Amélioration ciblée de la qualité des soins et de la qualité dans les domaines prioritaires d'investissement des ASC |  | BIRCH | 51145.84 |  | 2025-12-31 | 2025-12-31 | On track
Cote d'Ivoire | LMH | Amélioration ciblée de la qualité des soins et de la qualité dans les domaines prioritaires d'investissement des ASC | Milestone 2: Opérationnalisation de la phase pilote de l’approche supervision renforcée des acteurs communautaire afin d’améliorer la performance des acteurs Definition: Phase 1: Formation en cascade du niveau central, région, district et aires de santé( IDE, encadreurs et ASC) : rapports de formation (2024) Phase 2: Mise en oeuvre de la supervision renforcée : Rapports des activités de la phase pilote (2025) | BIRCH | 20152.73 |  | 2024-12-31 | 2024-12-31 | On track | Already completed, awaiting supporting documentation before changing the status
Cote d'Ivoire | LMH | Amélioration ciblée de la qualité des soins et de la qualité dans les domaines prioritaires d'investissement des ASC |  | BIRCH | 16970.96 |  | 2025-10-31 | 2025-10-31 | On track
Cote d'Ivoire | LMH | Cadre juridique des ASC établi | Milestone: Examen et analyse de la réglementation et des politiques avec toutes les parties prenantes Definition: Rapport de l'atelier de haut niveau sur le statut des ASC sur la base du rapport de l'analyse situationnelle conduite par l'ONG ALLIANCE CÔTE D'IVOIRE | BIRCH | 15260.25 |  | 2025-03-26 | 2025-03-26 | On track
Cote d'Ivoire | LMH | Des plans opérationnels détaillés et chiffrés pour la mise en œuvre de la stratégie nationale de santé communautaire, couvrant au moins les activités de CHW dans les subventions de fonds mondiaux pour faciliter la mise en œuvre des investissements CHW financés par les subventions de fonds mondiaux. | Milestone 1: Actualisation et finalisation du plan opérationnel intégré 2024 du PSNSC 2022-2025 Definition: Plan opérationnel 2024 du PSNSC 2022-2025 actualisé, Rapports de réunions | BIRCH | 23085 |  | 2024-03-31 | 2024-03-31 | Complete |  |  |  | ToR Operational plan development workshop; 2024 operational plan of the 2022-2025 Community Health national strategic plan
Cote d'Ivoire | LMH | Des plans opérationnels détaillés et chiffrés pour la mise en œuvre de la stratégie nationale de santé communautaire, couvrant au moins les activités de CHW dans les subventions de fonds mondiaux pour faciliter la mise en œuvre des investissements CHW financés par les subventions de fonds mondiaux. | Milestone 2: Élaboration de drafts de plans opérationnels régionaux en collaboration avec les parties prenantes Definition: Phase 1: Orientations des regions et districts : Rapport sur l'orientation des régions et districts (2024, 2025) Phase 2: Ateliers de validation des plans : Les premiers drafts des plans opérationnels régionaux (2024, 2025) | BIRCH | 55419.04 |  | 2024-10-30 | 2024-12-31 | On track | Consultant recruted, Concept note will be developped before contract signature
Cote d'Ivoire | LMH | Des plans opérationnels détaillés et chiffrés pour la mise en œuvre de la stratégie nationale de santé communautaire, couvrant au moins les activités de CHW dans les subventions de fonds mondiaux pour faciliter la mise en œuvre des investissements CHW financés par les subventions de fonds mondiaux. |  | BIRCH | 8412.48 |  | 2025-10-30 | 2025-10-30 | On track
Cote d'Ivoire | LMH | Des plans opérationnels détaillés et chiffrés pour la mise en œuvre de la stratégie nationale de santé communautaire, couvrant au moins les activités de CHW dans les subventions de fonds mondiaux pour faciliter la mise en œuvre des investissements CHW financés par les subventions de fonds mondiaux. | Milestone 3: Validation finale des plans opérationnels régionaux détaillé en collaboration avec les parties prenantes Definition: Les Plans opérationnels finaux et validés (2024) Rapports d’activités et d’atelier (2025) | BIRCH | 75405.71 |  | 2024-11-30 | 2024-12-31 | On track
Cote d'Ivoire | LMH | Des plans opérationnels détaillés et chiffrés pour la mise en œuvre de la stratégie nationale de santé communautaire, couvrant au moins les activités de CHW dans les subventions de fonds mondiaux pour faciliter la mise en œuvre des investissements CHW financés par les subventions de fonds mondiaux. |  | BIRCH | 7918.16 |  | 2025-10-31 | 2025-10-31 | On track
Cote d'Ivoire | LMH | Évaluation des capacités des directions concernées du ministère de la santé (SC/RHS) et élaboration et mise en œuvre d'un plan de renforcement des capacités sur mesure | Milestone 1: Élaboration d'un draft de rapport d'évaluation des capacités des directions et des programmes nationaux de santé du ministère de la santé concernées par la santé communautaire et des plans de renforcement/amélioration des capacités Definition: Draft de rapport d'évaluation des capacités pour les directions et programmes nationaux de santé du ministère de la santé (2024 et 2025) | BIRCH | 14468.78 |  | 2024-11-30 | 2025-03-31 | On track | [Muso Health has proposed to push these milestones to 2025] OK CFP [Claudia: will the 2024 amounts be used up?]
Cote d'Ivoire | LMH | Évaluation des capacités des directions concernées du ministère de la santé (SC/RHS) et élaboration et mise en œuvre d'un plan de renforcement des capacités sur mesure |  | BIRCH | 10184.4 |  | 2025-11-30 | 2025-11-30 | On track
Cote d'Ivoire | LMH | Évaluation des capacités des directions concernées du ministère de la santé (SC/RHS) et élaboration et mise en œuvre d'un plan de renforcement des capacités sur mesure | Milestone 2: Élaboration des Termes de Référence d’évaluation des capacités des directions et des programmes nationaux de santé du ministère de la santé concernées par la santé communautaire Definition: Les TDR de l'évaluation des capacités des directions du ministère de la santé concernées par la santé communautaire, soumis (2024, 2025) | BIRCH | 12602.39 |  | 2024-09-30 | 2024-11-30 | On track | Agree with Muso to develop the Concept note in Q4 2024, but other milestones rescheduled in 2025. [Muso Health has proposed to push these milestones to 2025]. Ok for CFP [Claudia: will the 2024 amounts be used up] [Desire: to ensure that the concept notes are in place]
Cote d'Ivoire | LMH | Évaluation des capacités des directions concernées du ministère de la santé (SC/RHS) et élaboration et mise en œuvre d'un plan de renforcement des capacités sur mesure |  | BIRCH | 11216.64 |  | 2025-10-31 | 2025-10-31 | On track
Cote d'Ivoire | LMH | Évaluation des capacités des directions concernées du ministère de la santé (SC/RHS) et élaboration et mise en œuvre d'un plan de renforcement des capacités sur mesure | Milestone 3: Suivi de la mise en oeuvre du Plan de renforcement/amélioration des capacités Definition: Rapports de suivi du plan de renforcement des capacités | BIRCH | 9049.88 |  | 2025-11-30 | 2025-11-30 | On track
Cote d'Ivoire | LMH | Évaluation des capacités des directions concernées du ministère de la santé (SC/RHS) et élaboration et mise en œuvre d'un plan de renforcement des capacités sur mesure | Milestone 4: Validation du rapport d'évaluation des capacités des directions et des programmes nationaux de santé du ministère de la santé concernées par la santé communautaire et des plans de renforcement/amélioration des capacités Definition: Rapport final d'évaluation des capacités des directions du ministère de la santé concernées par la santé communautaire Plans de renforcement/amélioration des capacités | BIRCH | 15826.05 |  | 2024-11-25 | 2025-03-31 | On track | [Muso Health has proposed to push these milestones to 2025] OK CFP [Claudia: will the 2024 amounts be used up]
Cote d'Ivoire | LMH | Rapports de suivi trimestriels sur la mise en œuvre des investissements dans la santé communautaire (sur la base de plans de mise en œuvre détaillés), y compris l'identification des goulots d'étranglement en matière de programmation et de capacité d'absorption, la résolution des problèmes et leur résolution dans les régions ciblées. | Milestone 1: Élaboration d'une feuille de route du suivi trimestriel des investissements du Fomds mondial en santé communautaire Definition: Rapport de l'atelier d'élaboration de la feuille de route du suivi trimestriel des investissements du Fomds mondial en santé communautaire GC7/C19RM (2024, 2025) La feuille de route du suivi trimestriel des investissements du Fomds mondial en santé communautaire (2024, 2025) | BIRCH | 31234.32 |  | 2024-04-30 | 2024-04-30 | Complete |  |  |  | Workshop report; BIRCH/IS +GC7/C19RM investment in CH (2024) quaterley review tool
Cote d'Ivoire | LMH | Rapports de suivi trimestriels sur la mise en œuvre des investissements dans la santé communautaire (sur la base de plans de mise en œuvre détaillés), y compris l'identification des goulots d'étranglement en matière de programmation et de capacité d'absorption, la résolution des problèmes et leur résolution dans les régions ciblées. |  | BIRCH | 21580.16 |  | 2025-10-30 | 2025-10-30 | On track
Cote d'Ivoire | LMH | Rapports de suivi trimestriels sur la mise en œuvre des investissements dans la santé communautaire (sur la base de plans de mise en œuvre détaillés), y compris l'identification des goulots d'étranglement en matière de programmation et de capacité d'absorption, la résolution des problèmes et leur résolution dans les régions ciblées. | Milestone 2: Réunion trimestrielle de suivi de la mise en œuvre du plan opérationnel intégré 2024 Definition: Rapport de suivi trimestriel y compris le plan de résolution des obstacles en 2024 | BIRCH | 18366 |  | 2024-12-31 | 2024-12-31 | On track | Online meeting
Cote d'Ivoire | LMH | Cartographie annuelle des investissements dans la santé communautaire par rapport à la stratégie nationale de santé communautaire (y compris l'intégration de la cartographie des investissements dans la santé communautaire dans les processus nationaux de cartographie des ressources et de suivi des dépenses). |  | SI | 15456 |  | 2025-03-25 | 2025-03-25 | On track
Cote d'Ivoire | LMH | Cartographie annuelle des investissements dans la santé communautaire par rapport à la stratégie nationale de santé communautaire (y compris l'intégration de la cartographie des investissements dans la santé communautaire dans les processus nationaux de cartographie des ressources et de suivi des dépenses). |  | SI |  |  | 2025-03-25 | 2025-03-25 | On track
Cote d'Ivoire | LMH | Cartographie annuelle des investissements dans la santé communautaire par rapport à la stratégie nationale de santé communautaire (y compris l'intégration de la cartographie des investissements dans la santé communautaire dans les processus nationaux de cartographie des ressources et de suivi des dépenses). | Milestone 2: Élaboration des Termes de référence de la suite de la cartographie annuelle des investissements dans la santé communautaire par rapport à la stratégie nationale de santé communautaire Definition: Les TDR de la suite de la cartographie annuelle des investissements dans la santé communautaire par rapport à la stratégie nationale de santé communautaire (2024, 2025) | SI | 18944.18 |  | 2024-12-27 | 2024-12-27 | On track
Cote d'Ivoire | LMH | Cartographie annuelle des investissements dans la santé communautaire par rapport à la stratégie nationale de santé communautaire (y compris l'intégration de la cartographie des investissements dans la santé communautaire dans les processus nationaux de cartographie des ressources et de suivi des dépenses). |  | SI | 17077.5 |  | 2025-10-31 | 2025-10-31 | On track
Cote d'Ivoire | LMH | Cartographie annuelle des investissements dans la santé communautaire par rapport à la stratégie nationale de santé communautaire (y compris l'intégration de la cartographie des investissements dans la santé communautaire dans les processus nationaux de cartographie des ressources et de suivi des dépenses). | Milestone 3: Finalisation du rapport de l'analyse situationnelle et l'élaboration de la cartographie des ressources/Investissement de la santé communautaire Definition: Le rapport de l'analyse situationnelle de la cartographie des ressources/Investissement de la santé communautaire | SI | 41702 |  | 2025-03-25 | 2025-03-25 | On track
Cote d'Ivoire | LMH | Cartographie annuelle des investissements dans la santé communautaire par rapport à la stratégie nationale de santé communautaire (y compris l'intégration de la cartographie des investissements dans la santé communautaire dans les processus nationaux de cartographie des ressources et de suivi des dépenses). |  | SI |  |  | 2025-03-25 |  | On track
Cote d'Ivoire | LMH | Cartographie annuelle des investissements dans la santé communautaire par rapport à la stratégie nationale de santé communautaire (y compris l'intégration de la cartographie des investissements dans la santé communautaire dans les processus nationaux de cartographie des ressources et de suivi des dépenses). | Milestone 4: Validation et diffusion de la carte annuelle des ressources axée sur les investissements dans les services de santé communautaires Definition: La carte annuelle des ressources axée sur les investissements dans les services de santé communautaire Rapport de diffusion des résultats | SI | 38259 |  | 2025-03-25 | 2025-03-25 | On track
Cote d'Ivoire | LMH | Évaluation annuelle de la maturité des systèmes des ASC | Milestone 1: Évaluation finale validée de la maturité des ASC et diffusion Definition: Rapport final validé de l'évaluation de la maturité des ASC incluant le plan d'action; le rapport de l'atelier d'évaluation de la maturité des ASC. (2024, 2025) | SI | 29002.75 |  | 2024-12-30 | 2024-12-30 | On track
Cote d'Ivoire | LMH | Évaluation annuelle de la maturité des systèmes des ASC |  | SI | 29002.75 |  | 2025-12-30 | 2025-12-30 | On track
Cote d'Ivoire | LMH | Évaluation annuelle de la maturité des systèmes des ASC | Milestone 2: Rencontres du Groupe Technique de Travail Santé Communautaire avec toutes les parties prenantes pour la validation des TDR de l'évaluation du modele de maturité Definition: TDR de l’évaluation validés par toutes les parties prenantes, Version préliminaire du rapport de l'évaluation de la maturité et Rapports des rencontres du GTT (2024, 2025) | SI | 11501.84 |  | 2024-11-30 | 2024-11-30 | On track
Cote d'Ivoire | LMH | Évaluation annuelle de la maturité des systèmes des ASC |  | SI | 11501.84 |  | 2025-11-30 | 2025-11-30 | On track
Cote d'Ivoire | LMH | Évaluation annuelle de la maturité des systèmes des ASC | Milestone 3: Suivi trimestriel des progrès Definition: Rapport trimestriel sur l'état d'avancement de la mise en œuvre du plan d'action (2024, 2025) | SI | 565.52 |  | 2024-10-31 | 2024-10-31 | On track
Cote d'Ivoire | LMH | Évaluation annuelle de la maturité des systèmes des ASC |  | SI | 1131.05 |  | 2025-12-31 | 2025-12-31 | On track
Cote d'Ivoire | LMH | Plan de financement durable à long terme (8-10 ans) et plan de mobilisation des ressources pour la santé communautaire / les agents de santé communautaire | Milestone 1: Élaboration d'un projet de plan de financement durable et d'un plan de mobilisation des ressources avec l’ensemble des parties prenantes Definition: Phase 1: collecte des données et analyse situationnelle (2024) Phase 2: Projet de plan de financement durable et de plan de mobilisation des ressources (2025) | SI | 42047.62 |  | 2024-10-25 | 2024-10-25 | On track | Concept note under developement & Phase 1 (data collection and situational analysis) to be completed in Q4 2024 [to revise timelines]
Cote d'Ivoire | LMH | Plan de financement durable à long terme (8-10 ans) et plan de mobilisation des ressources pour la santé communautaire / les agents de santé communautaire |  | SI | 2423.26 |  | 2025-03-30 | 2024-10-25 | On track | Discussion with Muso (to started ealier in Q4 2024 or 2025, first step of the process)
Cote d'Ivoire | LMH | Plan de financement durable à long terme (8-10 ans) et plan de mobilisation des ressources pour la santé communautaire / les agents de santé communautaire | Milestone 2: Élaboration des Termes de référence du plan de financement durable à long terme Definition: TDR du plan de financement durable à long terme (2025) | SI | 16675 |  | 2025-10-30 | 2025-10-30 | On track
Cote d'Ivoire | LMH | Plan de financement durable à long terme (8-10 ans) et plan de mobilisation des ressources pour la santé communautaire / les agents de santé communautaire | Milestone 3: Validation du plan de financement durable et du plan de mobilisation des ressources avec l’ensemble des parties prenantes et diffusion Definition: Phase 1: Plan de financement durable à long terme validé (2025) Phase 2: Plan de mobilisation des ressources validé (2025) | SI | 15826 |  | 2025-12-31 | 2025-12-31 | On track
Cote d'Ivoire | LMH | Stratégie nationale de santé communautaire actualisée et chiffrée | Milestone 1: Analyse situationnelle et organisation d'une revue de l’actuel plan stratégique détaillé chiffré Definition: Rapport complet de l'analyse situationnelle et de la revue à mi parcours du plan stratégique de la santé communautaire. Rapport de l'analyse situationnelle et de la revue du PSNSC 2022-2025 | SI | 91102 |  | 2025-05-30 | 2025-05-30 | On track
Cote d'Ivoire | LMH | Stratégie nationale de santé communautaire actualisée et chiffrée | Milestone 2: Diffusion du Plan Stratégique National de la Santé Communautaire révisé et validé Definition: Plan de diffusion validé, Rapports d’activités | SI | 26168 |  | 2025-12-31 | 2025-12-31 | On track
Cote d'Ivoire | LMH | Stratégie nationale de santé communautaire actualisée et chiffrée | Miestone 3: Elaboration de la stratégie nationale révisée et de calcul des coûts Definition: Draft du Plan Stratégique National de la Santé Communautaire révisée Rapports de rencontres et réunions Cadre/outil de modélisation des coûts | SI | 199649.29 |  | 2025-11-30 | 2025-11-30 | On track
Cote d'Ivoire | LMH | Stratégie nationale de santé communautaire actualisée et chiffrée | Milestone 4: Élaboration des grandes lignes de la stratégie par le GTT santé communautaire existant Definition: Rapport des réunions du GTT prenant en compte les nouvelles orientations stratégiques de la santé communautaire | SI | 15251 |  | 2025-05-30 | 2025-05-30 | On track
Ethiopia | LMH | Review and revision of national scope of practice and training package for PHC workforce (including CHWs and their supervisors) | Milestone 1: Blended learning content for IRT modules for HEWs accredited by CPD unit of HRD Definition: Evidence of accreditation by HRD | BIRCH | 28427 |  | 2024-06-30 | 2024-09-30 | Delayed | This activity was delayed because it was dependent on funds from the GC7 grant which was only signed in July 2024. The accreditation workshop is now conducted and MoH and other stakeholders have made inputs to the curriculum. LMH is finalizing the feedback working to get the accreditation. There is no need to reprogram this milestone. | 2024-08-01 | 2024-09-30
Ethiopia | LMH | Review and revision of national scope of practice and training package for PHC workforce (including CHWs and their supervisors) | Milestone 2: Supervision conducted in all regions to ensure quality of blended learning Definition: Supervision reports from onsite supervision visits | BIRCH | 45939 |  | 2024-12-30 | 2024-12-30 | On track | This activity was dependent on MoH's and RHBs' schedule of blended training. MoH has now sent budgets to regions for trainings to be undertaken and training schedules have also been shared. LMH has has so far underkaen 4 out of the planned 8 supervisions in the 8 target regions for the trainings. The rest of the supervision visits will be concluded by December 2024. No need for reprogramming | 2024-06-01 | 2024-12-31
Ethiopia | LMH | Review and revision of national scope of practice and training package for PHC workforce (including CHWs and their supervisors) | Milestone 3: Individual learner's data summarized and provided to HEWs supervisors for informing post-training supervision. Definition: Developed guideline for training program evaluation | BIRCH | 19881 |  | 2024-12-30 | 2024-12-30 | On track | This activity will be done once blended trainings are started. Individual learner's data is now being generated during the trainings delivered in milestone one to inform program evaluation. No need to reprogram this activity. | 2024-06-01 | 2024-12-31
Ethiopia | LMH | Quarterly monitoring reports on implementation of community health investments (based on Detailed implementation plans) including identification of programmatic and absorption bottlenecks, problem solving and resolution in targeted regions | Milestone 1: Key performance indicators for community health investments identified Definition: Key perfromance indicators approved by MOH will be submitted as evidence for completion of this milestone. | BIRCH | 71217 |  | 2024-09-30 | 2024-09-30 | Complete | A validation workshop has been conducted with MoH's relevant teams on which the KPIs are reviewed. | 2024-07-01 | August 24-25 | KPIs Identified and Validated by MOH to track GC7 HEP priorities
Ethiopia | LMH |  | Milestone 2: Key performance indicators for community health investment are reviewed quarterly at national and sub-national level Definition: Reports of KPI review, bottlenecks identified and action plans developed presented as evidence. | BIRCH | 25621 |  | 2024-10-31 | 2024-10-31 | On track | ToR developed for guiding quarterly review meetings. Development of dashboard for KPI quarterly monitoring is is in progress. We have planned one review in October 2024 only out of the two planned. There is need to reporgam this milestone since only half of the planned activities will be achieved. | Aug 1-Sep 30 | 2024-10-31
Ethiopia | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone 1: Health Extension Program (HEP) priorities from GC7 grant are incorporated into the annual woreda based operational plan Definition: Annual woreda based operational plan compiled at the national level will be submitted as an evidence of milestone completion | SI | 56890 |  | 2024-08-30 | 2024-08-30 | Complete | Continous technical support have been provided to MoH to incorporate GC7 HEP priorities into the woreda based comprehensive annual plan. | 2024-07-01 | August 1-15
Ethiopia | LMH |  | Milestone 2: Annual priority HEP activities based on GC7 grant identified/compiled and validated by CE-PHC LEO Definition: HEP priority activites identified annually based on GC7 grant activities and validated by the MOH CE-PHC LEO will be presented as evidence | SI | 2241 |  | 2024-08-30 | 2024-08-30 | Complete | A validation workshop has ben conducted on which the plan is validated and approved by MoH relevant teams (HEP, planning, RSSH teams).
Ethiopia | LMH | Annual assessment of CHW systems maturity | Milestone 1: HEP system maturity assessment guideline developed Definition: HEP system maturity assessment guideline adpated for Ethiopian context, adpated guideline submitted as evidence | SI | 8692 |  | 2024-06-30 | 2024-06-30 | Complete | The draft maturity assessment guideline has been reviewed by internal team. A validation workshop has been conducted with MoH teams on which the guideline has been reviewed. | 2024-06-01 | August 15-25
Ethiopia | LMH |  | Milestone 2: Training of national and sub-national HEP teams on utilization of HEP maturity assessment tool completed Definition: Training report will be presented as evidence | SI | 12353 |  | 2024-07-30 | 2024-09-30 | Delayed | This activity was dependent upon the completion of the first milestone and it is yet to be completed in September 2024. This will happen in september, no need for reprogramming
Ethiopia | LMH |  | Milestone 3: Annual HEP system maturity assessment conducted at national level with an input from sub-national level Definition: HEP maturity assessment findings and improvement plan presented on Annual national HEP performamce review-meeting; HEP system maturity assessment reports presented as evidence | SI | 33201 |  | 2024-09-30 | 2024-09-30 | On track | This activity is earmarked to be completed in September 2024 (No need for reprogramming, this will happen as planned).
Ethiopia | LMH | Long-term (8-10 year) sustainable financing plan and resource mobilization plan for community health / community health workers | Milestone 1: A national HEPO funding gap analysis with input from sub-national level conducted Definition: HEPO funding gap analysis report | SI | 4140 |  | 2024-12-30 | 2024-12-30 | On track | Procurement of consultancy services for financial data collection and analysis is in progress. ToR development and consultant identification is complete and the milestone will be completed as planned. There is no need for reprogramming
Ethiopia | LMH |  | Milestone 2: Data collection conducted for HEPO funding gap analysis Definition: Data collection on resources allocated for HEP will be conducted at national level from the strategic affairs office and CE-PHC LEO with an input from all regional health bureaus | SI | 47007 |  | 2024-12-30 | 2024-12-30 | On track | This will happen this year through workshop and fieldwork in October while analysis and interpretation will happen next year and will be included in next year's budget separately. (No need for reprogramming) | 2024-08-01 | 2024-12-01
Ethiopia | LMH | Annual mapping of investments in community health against the national community health strategy (including integration of community health investment mapping into national Resource Mapping and Expenditure Tracking processes) | Milestone: High-level annual mapping of investments on HEP conducted Definition: Mapping of investments on community health will be conducted at the MoH level in close collaboration with the CE-PHC and Strategic Affairs LEO's based on the data collected on resource allocation for HEP | SI | 48994 |  | 2024-09-30 | 2024-12-01 | On track | same as above - this will happen this year through workshop and fieldwork in October while analysis and interpretation will happen next year and will be included in next year's budget separately. (No need for reprogramming) | 2024-08-01 | 2024-12-01
Ghana | LMH | Annual assessment of CHW systems maturity | Milestone: CHWs systems maturity assessment conducted through various stakeholder engagements and consultations. Definition: Maturity assessment report (2024, 2025) | BIRCH | 14807 |  | 2024-11-30 | 2024-11-30 | On track
Ghana | LMH |  |  | BIRCH | 24522 |  | 2025-12-31 | 2025-12-31 | On track
Ghana | LMH | Annual mapping of investments in community health against the national community health strategy (including integration of community health investment mapping into national Resource Mapping and Expenditure Tracking processes) | Milestone: Annual resource mapping of current and planned investments in Network of Practice and SDSI conducted. Definition: 1. Concept note for resource mapping (2024) 2. Resource map developed (2024) 3. Meeting notes from stakeholder engagements (2024, 2025) | BIRCH | 20959 |  | 2024-11-30 | 2024-11-30 | On track
Ghana | LMH |  |  | BIRCH | 24372 |  | 2025-11-30 | 2025-11-30 | On track
Ghana | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone 1: Costed operational plan for SDSI, indicating activities, cost and timelines for GF funding for community health developed. Definition: Finalised costed operational plan for SDSI. | BIRCH | 46002 |  | 2024-10-31 | 2024-10-31 | On track
Ghana | LMH |  | Milestone 2: District prioritization analysis updated with relevant disease and PHC indicators to inform prioritization of geographies and subsequent allocation of Global Fund community health investments for the SDSI. Definition: Report on prioritization analysis. | BIRCH | 45926 |  | 2024-06-05 | 2024-06-05 | Complete | Only awaiting final report, they shared the slide version of the report earlier
Ghana | LMH |  | Milestone 3: Inception meeting for project implementation held. Definition: 1. Finalised work plan. 2. Meeting notes. | BIRCH | 28300 |  | 2024-07-17 | 2024-07-17 | Delayed
Ghana | LMH |  | Milestone 4: Sub-district level needs assessment conducted across prioritised geographies to understand gaps and costs that will be required for development of operational plan. Definition: Report on sub-district level needs assessment submitted (to inform the costed operational plan for SDSI implementation) | BIRCH | 47495 |  | 2024-06-15 | 2024-06-15 | Complete | Only awaiting final report, they shared the slide version of the report earlier
Ghana | LMH | Integrated HRH/CHW Strategic Plan | Milestone: National HRH Strategic Plan revised to include CHW Definition: 1. Evaluation of existing strategy 2. Revised HRH Strategy | BIRCH | 43422 |  | 2025-02-01 | 2025-02-01 | On track
Ghana | LMH | Long-term (8-10 year) sustainable financing plan and resource mobilization plan for community health / community health workers | Milestone: Sustainable financing and resource mobilization plan developed for community health systems Definition: 1. Concept note 2. Meeting notes 3. Draft financing plan | BIRCH | 83475 |  | 2025-09-30 | 2025-09-30 | On track
Ghana | LMH | Quarterly monitoring reports on implementation of community health investments (based on Detailed implementation plans) including identification of programmatic and absorption bottlenecks, problem solving and resolution in targeted regions | Milestone 1: Quarterly operational plans developed to guide GHS to monitor GC7 and C19RM community health investments Definition: Quarterly operational plan | BIRCH | 43625 |  | 2024-07-31 | 2024-07-31 | Delayed
Ghana | LMH |  | Milestone 2: Quarterly review meetings conducted with the GHS to review implementation progress and identify any bottlenecks to address. Definition: Quarterly review meeting reports (meeting notes and action plans) (2024, 2025) | BIRCH | 27537 |  | 2024-10-31 | 2024-10-31 | On track
Ghana | LMH |  |  | BIRCH | 49286 |  | 2025-12-31 | 2025-12-31 | On track
Ghana | LMH |  | Milestone 3: SDSI Coordination Framework/Monitoring approach developed Definition: SDSI coordination framework/monitoring approach | BIRCH | 29875 |  | 2024-07-15 | 2024-07-15 | Delayed | This is ongoing but due to delays for GF to approve the SDSI plan, they ahve to wait before develoing the monitoring framework
Ghana | LMH | Review and revision of national scope of practice and training package for PHC workforce (including CHWs and their supervisors) | Milestone 1: HRH Training Needs Assessment completed Definition: Training needs assessment report | BIRCH | 75108 |  | 2025-03-15 | 2025-03-15 | On track
Ghana | LMH |  | Milestone 2: HRH Training Plan developed Definition: Training plan | BIRCH | 48351 |  | 2025-07-30 | 2025-07-30 | On track
Ghana | LMH | Updated and costed national community health strategy | Milestone 1: CHPS implementation guidelines reviewed and updated Definition: 1. Review reports 2. Meeting notes | BIRCH | 55662 |  | 2024-10-30 | 2024-10-30 | On track
Ghana | LMH |  | Milestone 2: CHPS implementation guidelines validated by stakeholders Definition: Meeting notes and updated CHPS implementation guidelines | BIRCH | 41275 |  | 2024-12-31 | 2024-12-31 | On track
Guinea | LMH | Amélioration ciblée de la qualité des soins et de la qualité dans les domaines prioritaires d'investissement des ASC | Milestone 1: Un document d’orientation sur la mise en place de structures de gouvernance de la santé communautaire au niveau communautaire est élaboré Definition: TDR atelier, document d'orientation | BIRCH | 32729.4 |  | 2024-11-30 | 2024-11-30 | On track | In July, alongside the pilot project of integration of CH in municipalities PAI/PDLvalidation workshop, this milestone was discussed and a draft of the structure of the document to be produced was developed. Will be finalized by the due date | 2024-07-01
Guinea | LMH |  | Milestone 2: Un rapport semestriel/trimestriel d’appui au fonctionnement des plateformes de coordination de la santé au niveau décentralisé est disponible Definition: TDR, Rapports réunion des plateformes de coordination de la santé communautaire au niveau décentralisé | BIRCH | 45563.65 |  | 2024-12-31 | 2024-12-31 | On track | 3 sessions planned in 2024 but with regard to workplanning process, ony 2 sessions will be organized. The First session organized in August 2024. Second session planned in Q4. Savings expected [The three sessions will not be possible; one inJuly, 2nd one towards the end of the year] [what's the savings --> approx $15k] | 2024-07-01
Guinea | LMH | Évaluation annuelle de la maturité des systèmes des ASC | Milestone: Les outils d’évaluation de la maturité du système pour la prestation de santé par les ASC/Reco sont adaptés et adoptés au niveau national Definition: Outils d'évaluation de la maturité validés, rapport de l'atelier d'adaption et d'adoption | BIRCH | 12348.6 |  | 2024-09-30 | 2024-09-30 | On track | ToR was developed and is on validation by CH division. workshop, panned in september. After that, Need to plan the maturity assessment as this should now be completed in 2024 (initialy planned in Q1 2025) Additionnal budget will be required. Yann & Désiré to agree on how to support Gunea & BFA to avoid delay [Peter: leverage the savings from QoC; why the delay if the docs are already in place and used last year --> availability for the adoption of the tool --> can we discuss the possibility of Yann/Pierre supporting]
Guinea | LMH | Plan de déploiement de la main-d'œuvre des SSP | Milestone: Un plan de déploiement de la main d'oeuvre des SSP incluant les ASC/Reco est disponible Definition: TDR, plan de déploiement de la main d'oeuvre des SSP incluant les ASC/RECO | BIRCH | 5529.7 |  | 2024-11-30 | 2024-11-30 | On track | ToR to be developped
Guinea | LMH | Plan de financement durable à long terme (8-10 ans) et plan de mobilisation des ressources pour la santé communautaire / les agents de santé communautaire | Milestone 1: Le document du projet pilote d’intégration de la santé communautaire dans les PDL/PAI des communes soutenues par le Fonds mondial est développé et validé en fin avril 2024 Definition: Projet pilote d'intégration de la SC dans les PDL/PAI des communes soutenues par le FM | BIRCH | 14007.27 |  | 2024-04-30 | 2024-04-30 | Complete |  | 2024-04-01 | 2024-08-01 | Pilot project of integration of CH in the PDL/PAI of ten GF supported municipalities in Guinea
Guinea | LMH |  | Milestone 2: Le rapport de capitalisation/documentation des bonnes pratiques du projet pilote sur l’intégration de la santé communautaire dans les PDL/PAI des communes soutenues par le Fonds mondial est disponible Definition: TDR, rapport de capitalisation des bonnes pratiques du projet pilote | BIRCH | 77523.6 |  | 2024-12-31 | 2025-02-28 | On track | This milestone will be repeated in the 2025 work plan because the pilot project will be extented over December 2024 because of the delay. The national process of developing municipalities annual investment plans should have already started but their is a delay because of political situation (new head of municipalities nominated recently). 6 activities planned in 2024 but 3 are feasiable. The remaining activities to be completed by end of february 2025 (Estimated carryover budget in 2025=30-40,000$) . IP will start developing ToR and tools for municipalities staffs trainings as well as supervision ToR..A document under developement to guide capitalisation & evidences generation to support scaling up.
Guinea | LMH |  | Milestone 3: Le rapport de l’atelier de concertation avec le MEF, MB, Parlement, MATD, MSHP autour de l’intégration de la santé communautaire dans le budget 2025 est disponible Definition: TDR, dossiers de plaidoyer,rapport de l'atelier de concertation | BIRCH | 57626.8 |  | 2024-06-30 | 2024-11-30 | Delayed | Draft of ToR developped, waiting supporting documentation. IH will finalise the consultant recruitment processus. CFP will support ToR finalisation and the consultant recruitment process
Guinea | LMH |  | Milestone 4: Le rapport sur le forum et le rapport de l'enquête d’impact du forum sur la compréhension et l'intérêt des parties prenantes et en particulier les communes pour l'opérationnalisation de la santé communautaire sont disponibles un mois après la tenue du forum national sur le financement pérenne de la santé communautaire Definition: Les rapports du forum consultatif, du consultant international, de l'évaluation de l'impact du forum auprès des participants, la feuille de route pour la mise en oeuvre des recommandation du forum, | BIRCH | 38853.1 |  | 2024-05-30 | 2024-05-30 | Complete |  | 2024-01-01 | 2024-05-01 | Rapport synthèse du forum consultatif; Feuille de route Forum; Rapports du consultant international; Rapport de l'évaluation de l'impact du forum auprès des participants; Feuille de route pour la mise en oeuvre des recommandation du forum Rapport cartographie du flux de financement de la santé communautaire en Guinée
Guinea | LMH |  | Milestone 5: Les capacités et compétences d’une organisation locale de la société civile sont renforcées pour assurer une pérennité dans le transfert des connaissances en matière d’appui aux communes pour intégrer la santé communautaire dans leur budget Definition: TDR, Rapports de renforcement des capacités d'une organisation locale | BIRCH | 9427 |  | 2024-06-30 | 2024-12-31 | Delayed | Local organization selection on the process of finalization. The capacity building will be alongide the pilot project implementation Consider to develop the recruitment criteria for the local organization - assessment; DD
Guinea | LMH |  | Milestone 6: Un Plan de gestion sur le financement durable de la santé communautaire en Guinée est développé et finalisé en fin avril 2024 (simultanément avec le plan opérationnel sur la cartographie des financements de la santé communautaire) Definition: Plan de gestion sur le financement durable de la SC | BIRCH | 10802 |  | 2024-04-30 | 2024-10-31 | Delayed | A draft of micro plan is available: first version developped in april, was improved by GFCT health financing specialist. Orientation session in planning in september for Guinea team. The process is currently supported by the international consultant who supported the CH forum organization in Q2. |  |  | Draft (no review needed )
Guinea | LMH | Plans opérationnels détaillés et chiffrés pour la mise en œuvre de la stratégie nationale de santé communautaire, couvrant au minimum les activités des ASC dans les subventions du Fonds mondial afin de faciliter la mise en œuvre des investissements des ASC financés par les subventions du Fonds mondial. | Milestone 1: Un plan opérationnel détaillé et budgétisé de mise en œuvre des activités du Plan stratégique national santé communautaire en Guinée est disponsible Definition: TDR, plan opérationnel détaillé et budgétisé, rapport de l'atelier d'élaboration | BIRCH | 25390.75 |  | 2024-12-31 | 2024-12-31 | On track
Guinea | LMH |  | Milestone 2: Une note conceptuelle pour guider l’élaboration d’un plan opérationnel de la mise en œuvre des activités du Plan stratégique national santé communautaire est développée et validée d’ici le 30 avril 2024. Definition: Note conceptuelle de l'élaboration d'un plan opérationnel de mise en oeuvre de la stratégie nationale de santé communautaire | BIRCH | 785.57 |  | 2024-06-30 | 2024-10-31 | Delayed | CFP will support concept note drafting by end of september, validation to plan in october
Guinea | LMH | Rapports de suivi trimestriels sur la mise en œuvre des investissements dans la santé communautaire (sur la base de plans de mise en œuvre détaillés), y compris l'identification des goulots d'étranglement en matière de programmation et de capacité d'absorption, la résolution des problèmes et leur résolution dans les régions ciblées. | Milestone 1: Un plan d'action/assistance technique trimestriel est disponible Definition: Plan d'assistance technique trimestrielle | BIRCH | 16157.68 |  | 2024-12-31 | 2024-12-31 | On track
Guinea | LMH |  | Milestone 2: Un rapport de supervision trimestrielle de la mise en œuvre du Plan stratégique national santé communautaire est disponible Definition: TDR, rapport de supervision trimestrielle de la mise en oeuvre du plan opérationnel | BIRCH | 74496.6 |  | 2024-12-31 | 2024-12-31 | On track | 2 main activities planned under this milestone: 1) One visit (IH +CCM) for strategic monitoring of GF investments in community health in the regions of the country 2) Quarterly joint supervision of community health activities with CH division and PR): 3 sessions planned but only one session possible in 2024. Savings expected
Guinea | LMH | Surveillance communautaire basée sur les événements (prestation à définir avec le ministère de la santé et les prestataires d'assistance technique SONAR+BIRCH dans les pays concernés) | Milestone: Un guide national de la surveillance base sur les évènements est élaboré Definition: Guide national validé, rapport atelier de validation du Guide | BIRCH | 16061.52 |  | 2024-08-31 | 2024-12-31 | Delayed | Discussions ongoing between stakeholders: SONAR/TFGH, ANSS and IH. ToR developed for the recruitment of the national consultants that will to support the process.
Kenya | LMH | Annual assessment of CHW systems maturity | Milestone 1: Annual assessment of CHW system maturity workshop Definition: Report on the Annual CHW systems maturity assessment | SI | 13107 |  | 2024-07-31 | 2024-10-31 | Delayed | The concept note has been developed pending incorporation of CFP's comments to include the proposed timelines. The delay was occasioned by competing priority by a partner organisation Dates for KQMCH assessment: Sep 23 - 27
Kenya | LMH |  | Milestone 2: Tracking and monitoring performance of the CHW system maturity workshop Definition: Tracking and monitoring report of the CHW system maturity | SI | 13573 |  | 2024-10-31 | 2024-10-31 | On track | Dependent on timely finalization of above
Kenya | LMH | Annual mapping of investments in community health against the national community health strategy (including integration of community health investment mapping into national Resource Mapping and Expenditure Tracking processes) | Milestone 1: Annual analysis and tracking of community health expenditure Definition: Community health expenditure analysis and tracking report | SI | 6926 |  | 2024-07-31 | 2024-11-30 | Delayed | The team has commenced on the development of the CH financing landscape analysis( tracking CH investments 2021 - 2027) _ mapping of CH investments. The request for the period is based on the partners request to cover that period so that they can get information on the past and going forward. The team has also shared the same with the DCH and other partners for providing the CH investment data
Kenya | LMH |  | Milestone 2:CH investment and resource mapping Definition: CH investment and resource mapping report | SI | 5983 |  | 2024-07-31 | 2024-11-30 | Delayed | As above
Kenya | LMH | Capacity assessment of relevant MOH directorates (CH/HRH) and tailored capacity building plan developed and implemented | Milestone 1: Capacity building initiatives, response and strategies Definition: Capacity building plan | SI | 6006 |  | 2024-12-31 | 2024-12-31 | On track | Partner has started the preparatory work of developing the assessment tool
Kenya | LMH |  | Milestone 2: CH/HRH capacity assessment Definition: CH/HRH capacity assessment report | SI | 7875 |  | 2024-10-30 | 2024-12-31 | On track | As above
Kenya | LMH |  | Milestone 3: Support implementation of the capacity building plan Definition: Monitoring report on the impact of capacity building initiatives on directorate performance | SI | 5983 |  | 2024-12-31 | 2024-12-31 | On track | As above
Kenya | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone 1: Detailed and costed operational plan/AWP for FY 2024/25 Definition: Operational plan/AWP for FY2024/25 | SI | 9640 |  | 2024-07-30 | 2024-07-30 | Complete | AWP completed - Partner following up with DCH to get the signed off version
Kenya | LMH | Long-term (8-10 year) sustainable financing plan and resource mobilization plan for community health / community health workers | Milestone 1: CH financing landscape analysis Definition: CH financing landscape analysis report | SI | 11273 |  | 2024-11-30 | 2024-11-30 | On track | The team has commenced on the development of the CH financing landscape analysis (tracking CH investments 2021 - 2027) _ mapping of CH investments. The request for the period is based on the partners request to cover that period so that they can get information on the past and going forward. Additionally, the tool incorporates comments from a CH partner and the team has also shared the same with the DCH for comments
Kenya | LMH |  | Milestone 2: CH sustainable financing planning workshop Definition: Long term CH sustainable financing plan | SI | 19346 |  | 2024-12-31 | 2024-12-31 | On track | Dependent on finalization of milestone 1
Kenya | LMH |  | Milestone 3: Visioning workshop on CH/PHC financing sustainability Definition: CH/PHC visioning workshop report | SI | 5983 |  | 2024-12-31 | 2024-12-31 | On track | As above
Kenya | LMH | Quarterly monitoring reports on implementation of community health investments (based on Detailed implementation plans) including identification of programmatic and absorption bottlenecks, problem solving and resolution in targeted regions | Milestone 1: CH Stakeholder engagement to build consensus on analysis findings Definition: CH Stakeholder engagement report and action plan to address bottlenecks | SI | 12009 |  | 2024-10-30 | 2024-10-30 | On track | Partner has started the preparatory work of developing the concept note - Bottleneck analysis workshop from partners from a programmatic and investment perspective
Kenya | LMH |  | Milestone 2: Community Health programmatic and investment bottleneck analysis Definition: Community health programmatic and investment bottleneck analysis report | SI | 17782 |  | 2024-10-15 | 2024-10-15 | On track | As above
Kenya | LMH |  | Milestone 3: Quarterly CH stakeholder forum Definition: CH stakeholder forum report | SI | 8996 |  | 2024-10-30 | 2024-10-30 | On track | As above
Kenya | LMH | Targeted Quality of Care/Quality Improvement rolled out in priority areas of CHW investment | Milestone 1: Action/Improvement plan on the KQMCH areas of improvement Definition: KQMCH action/improvement plan | SI | 10583 |  | 2024-12-31 | 2024-12-31 | On track | Concept note & evaluation tool developed - A planning team is being set-up in partnership with the DCH to embark on the evaluation
Kenya | LMH |  | Milestone 2: Assessment report KQMCH implementation, (successes, challenges, lessons learnt and recommendations for improvement ) Definition: KQMCH assessment report | SI | 24038 |  | 2024-12-31 | 2024-12-31 | On track | As above
Kenya | LMH |  | Milestone 3: Digital KQMCH system for level 1 developed and linked to Kenya Health Information System 2 Definition: Certificate of completion of the digital system | SI | 22083 |  | 2024-12-31 | 2024-12-31 | On track | As above
Kenya | LMH |  | Milestone 4: eCHIS enhancement to include new CH modules such as the NCD Definition: Certificate of completion of the enhancement of eCHIS | SI | 13688 |  | 2024-12-31 | 2024-12-31 | On track | There is a risk of reprogramming this to 2025. This is a result of ongoing new modules being added to the current eCHIS as well as linking it to KHIS2 and competing priorities with other partners coupled by working with a lean DCH team Dependent on the deployment of NCD curriculum
Kenya | LMH |  | Milestone 5: Integration of eCHIS to other digital health systems such as the Master Facility List and Master Community Health Unit List Definition: Certificate of completion of the integration | SI | 10583 |  | 2024-12-31 | 2024-12-31 | On track | As above
Liberia | LMH | Quarterly monitoring reports on implementation of community health investments (based on Detailed implementation plans) including identification of programmatic and absorption bottlenecks, problem solving and resolution in targeted regions | Milestone 1: A validated quarterly monitoring tools for implementation of community health investment is completed by the MOH with technical support from LMH Definition: Validated versions of the quarterly monitoring tools for implementation are available | BIRCH | 31836.47 |  | 2024-10-31 | 2024-12-31 | On track | Co-Financing Monitoring Approach: The GF PUDR tool was adopted for tracking GF investment while The Ministry of Health’s Health Financing Unit (HFU) will collect GoL co-financing data using a modified RMET template, supported by Last Mile Health (BIRCH project) for analysis and reporting. Key outputs agreed upon include tracking PHC funds transfers, CHSS payroll transitions to government, and reporting on procurement and system development progress.
Liberia | LMH |  | Milestone 2:The quarterly monitoring tool is piloted in at least 2 counties and results are disseminated at 1 BRM meeting to solicit feedback to inform planning and implementation of community health interventions and inform community health investments Definition: Pilot results and feedback for planning and implementation are shared | BIRCH | 22123.18 |  | 2024-12-31 | 2024-12-31 | On track | Engagement ongoing with the LMH as the partners had requested for clarity on the CH investment tracking which they felt was a potential duplication with the PR disbursement report. It seemed there might be overlap with what the PR PUDR already covers (attached for reference). AFF has had discussions with the team on the same and currently waiting for LMH's direction on possible engagement with the PR to align on the reporting expectation. Biweekly check-in with the Health Financing Unit in the MoH to address any bottlenecks, information sharing [Waiting for any specific requests for support from AFF re the PR engagement] [we need to share a populated template]
Liberia | LMH | Functional national georeferenced CHW master list hosted in a registry | Milestone 1: Protocol and tools for geospatial mapping designed and validated by MOH and CH stakeholders Definition: Adopted validated protocol and tools for geospatial mapping | BIRCH | 9554.17 |  | 2024-07-31 | 2024-11-30 | Delayed | Development of Protocol and Tools for Geospatial Mapping: LMH facilitated a meeting to update the MoH on the geospatial mapping exercise and the recruitment of a consultant. The MoH, now led by the Health Financing Unit, raised concerns about the scope, outcome, and resource needs for mapping all PHC facilities, and requested to review the consultant’s TOR. The LMH is currently finalizing on the consultant's SoWs which they will share with Anthony - the GF Geospatial expert for review before sharing the same with the MoH team [confirm revised timeline]
Liberia | LMH |  | Milestone 2: Enumerators for data collection are recruited and trained Definition: All enumerators are trained in geospatial mapping as evidenced by a composite score of 75% and above in post-evaluation test results | BIRCH | 52605.93 |  | 2024-10-31 | 2024-11-30 | On track | This milestone is dependent on the completion of the first mielstone
Liberia | LMH |  | Milestone 3: The initial phase of Geospatial mapping data is collected across 5 counties. Definition: Data collected from the initial phase of Geospatial mapping | BIRCH | 263031.06 |  | 2024-12-31 | 2025-03-31 | On track | Same as above [look at the cost drivers; initiate implementation] [potentially split the budget from Q4 2024 to Q1 2025] [Caroline to confirm the timelines]
Liberia | LMH | Capacity assessment of relevant MOH directorates (CH/HRH) and tailored capacity building plan developed and implemented | Milestone 1: An annual capacity assessment tool targeting 4 MOH programs (CHSD, HFU, HRH and HMER) is co-designed with and validated by the MOH Definition: A validated capacity assessment tool is shared | BIRCH | 13492.34 |  | 2024-08-30 | 2024-11-30 | Delayed | This milestone is dependent upon the National Health System Capacity Assessment being validated and disseminated. The gaps identified in the assessment will be reviewed, and the findings will be used to guide the completion of this task. LMH is yet to share the latest status [the national health system capacity will be disseminated in Sep (week of the 16th]
Liberia | LMH |  | Milestone 2: An annual capacity assessment is conducted by LMH with generated data shared to inform capacity building plan development Definition: Finalized annual analyzed capacity assessment data is shared | BIRCH | 7673.01 |  | 2024-10-31 | 2024-12-31 | On track | This milestone is dependent on the completion of the first milestone [Confirm due dates with LMH]
Liberia | LMH |  | Milestone 3: A tailored capacity-building plan for each MOH program/unit is co-developed with the MOH and initiate implementation by Q1 2025 Definition: Final tailored co-designed capacity building plan is submitted | BIRCH | 13341.33 |  | 2024-12-31 | 2025-03-31 | On track | Same as above
Liberia | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone: A detailed Community Health costed operational plan is validated by MOH and community health stakeholders Definition: A validated community health costed operational plan is available | SI | 64335 |  | 2024-10-31 | 2024-12-31 | On track | Preliminary is yet to commence on this milestone [work has not started; we will need clarity on the status plus
Liberia | LMH | Annual assessment of CHW systems maturity | Milestone 1: Annual national level maturity assessment conducted and data generated is shared among stakeholders Definition:The final analyzed data from the maturity assessment is shared | SI | 67046.28 |  | 2024-10-31 | 2024-10-31 | On track | The team has finalized the assessment tool and shared the protocol/roadmap with key stakeholders for review. The agreed-upon timeline with MoH directors further demonstrates that the assessment is on track for completion and subsequent data sharing. LMH to share the latest status.
Liberia | LMH |  | Milestone 2: Final Annual CHW maturity assessment report compiled and submitted by the LMH and MOH team in December 2024 and 2025 Definition: The final maturity asssement report is submitted | SI | 5017.36 |  | 2024-12-31 | 2024-12-31 | On track | Dependent on the first milestone
Liberia | LMH |  | Milestone 3: A co-designed action plan aimed at addressing issues from the maturity assessment is validated by the MOH and stakeholders Definition:A validated plan of action based on the maturity assessment is available | SI | 2524.83 |  | 2024-11-29 | 2024-11-29 | On track | Dependent on the first milestone
Liberia | LMH |  | Milestone 4: County level engagements to discuss results among targeted counties and identify innovative approaches is conducted Definition: At least 5 regional level engagements conducted across Liberia's 5 health regions | SI | 21476.83 |  | 2024-12-27 | 2024-12-27 | On track | Dependent on the first milestone
Liberia | LMH | Annual mapping of investments in community health against the national community health strategy (including integration of community health investment mapping into national Resource Mapping and Expenditure Tracking processes) | Milestone 1: Annual NCHP resource mapping exercise conducted by MOH at the national level with good quality data analysed and uploaded to https://liberiahfu.zohocreatorportal.com/#Page:Customers_Activity_Page and reports shared Definition: Annual NCHP resource mapping reports completed | SI | 46887.9 |  | 2024-11-29 | 2024-12-31 | On track | All expenditure report from partners expected as the year comes to an end. LMH to leverage on this to build on this milestone [to confirm feasibility with the Provider]
Liberia | LMH |  | Milestone 2: MOH is supported to conduct the first annual NCHP resource expenditure performance tracking, process, analyse and share the report Definition: Annual NCHP resource expenditure performance tracking report is completed | SI | 8927.49 |  | 2024-12-20 | 2025-03-31 | On track | As above
Liberia | LMH |  | Milestone 3: Learnings from 2024 annual resource mapping and expenditure tracking exercises gathered and plan to incorporate in health sector RMET process and system Definition: Learnings from 2024 annual resource mapping and expenditure tracking exercises are available | SI | 10087.05 |  | 2024-12-31 | 2025-03-31 | On track | As above
Malawi | LMH | Annual assessment of CHW systems maturity | Milestone 1: Stakeholder engagement /consultation meeting on maturity assessment development Definition: Maturity assessment stakeholder engagement report | BIRCH | 3426 |  | 2024-09-15 | 2024-11-30 | Delayed | Preparations with MoH are underway to deliver this activity as per the planned revised dates. It will thus be completed as planned without any reprogramming.
Malawi | LMH |  | Milestone 2: CHW maturity assessment validated and disseminated Definition: Validated Communty Health Systems Maturity Assessment Report | BIRCH | 20641 |  | 2024-12-15 | 2024-12-15 | On track | same as above - the agreed dates for October to be agreed with MoH soon. No reprogramming is required.
Malawi | LMH | Annual mapping of investments in community health against the national community health strategy (including integration of community health investment mapping into national Resource Mapping and Expenditure Tracking processes) | Milestone: Technical assistance provided to conduct annual resource geo-mapping against costed NCHF Definition: Annual Community Health Resource mapping Report | BIRCH | 10157 |  | 2024-12-31 | 2024-12-31 | On track | Finalizing recruitment of Consultant to lead this exercise. Expected to report by September 19th. The recruited consultants (BIRCH Coordinator & Health Financing Consultant will accelerate the implementation of this activity starting next month. No reprogramming, work to commence between October – December 2024.
Malawi | LMH | Capacity assessment of relevant MOH directorates (CH/HRH) and tailored capacity building plan developed and implemented | Milestone 1: Capacity building plan for MOH directorates (CH/HRH) developed. Definition: Detailed terms of reference; signed contract; report with detailed capacity building plan | BIRCH | 9285 |  | 2024-04-30 | 2024-12-30 | Delayed | Currently in the final stages of recruiting capacity building consultant. A consultative meeting for developing a capacity-building plan is scheduled for October. No reprogramming is required.
Malawi | LMH |  | Milestone 2: MoH managers complete the capacity building /mentorship program Definition: Training/ mentorship materials; Mini -graduation ceremony | BIRCH | 19248 |  | 2024-11-30 | 2024-11-30 | On track | No clear indication of preliminary work done yet
Malawi | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone 1: Final Draft of Detailed and Cost Operational Plan developed Definition: Validated final costed operational plan | BIRCH | 17543 |  | 2024-05-30 | 31 October, 2024 | Delayed | This activity is complete. The validation workshop has just been concluded and LMH is finalizing inputs from the stakeholders. |  |  | Link
Malawi | LMH |  | Milestone 2: CHW Stakeholder engagement (TWG) meeting(s) conducted Definition: Meeting reports | BIRCH | 4087 |  | 2024-11-30 | 2024-11-30 | On track | This activity was dependent on the completion of milestone 1, it will now be conducted in October 2024.
Malawi | LMH | Quarterly monitoring reports on implementation of community health investments (based on Detailed implementation plans) including identification of programmatic and absorption bottlenecks, problem solving and resolution in targeted regions | Milestone 1: Quarterly district led supportive supervision conducted in Nsanje, Salima and Machinga (using Integrated supportive supervision tool) Definition: Quarterly supervision report, financial report | BIRCH | 66484 |  | 2024-12-31 | 2024-12-31 | On track | A total of three cycles of supportive supervision visits to the three districts were planned. So far, two cycles have been completed and the last cycle is planned for September and December 2024. No need for reprogramming.
Malawi | LMH |  | Milestone 2: Quarterly cluster based integrated (ICCM, CBNMC & ICHIS) review meetings and CLM initiatives conducted in Nsanje, Salima and Machinga Definition: Quarterly review meeting report, financial report | BIRCH | 47211 |  | 2024-11-30 | 2024-11-30 | On track | This is happening at district level to check how ichis is being used. Findings from supervision are discussed and assimilated. One meeting per district per quarter is the original plan. Only one meeting per district for one quarter (Q4) instead of the two planned quarters is likely to be undertaken. There is a need for reprogramming.
Malawi | LMH |  | Milestone 3: Community Health Monitoring information systematically managed for improved decision making Definition:ICHIS training manual reviewed. iCHIS dashboard optimized for reporting | BIRCH | 41666 |  | 2024-07-30 | 2024-09-30 | Complete | Four planned activities for this milestone were completed in the second quarter
Malawi | LMH |  | Milestone 4: Community Health Investments systematically monitored for improved service delivery Defintiion: Activity reports | BIRCH | 7567 |  | 2024-12-15 | 2024-12-15 | On track | No reprogramming is required since plans are underway to organise this event for November 2024
Malawi | LMH |  | Milestone 5: Quarterly review and feedback meetings conducted Defition: Quarterly review meeting reports | BIRCH | 8790 |  | 2024-12-30 | 2024-12-30 | On track | No reprogramming is required, this activity is planned for November to obtain feedback from MoH SMT and other stakeholders on the iCHIS and other data dashboards.
Malawi | LMH |  | Milestone 6: Community Health Facilities directly supported/ financed for improved service quality Definition: Audit reports | BIRCH | 18462 |  | 2024-12-31 | 2024-12-31 | On track | No need for reprogramming since this activity is already being implemented. LMH has so far supported MoH with the development of DFF training manual which will be used to train HCMCs in readiness for management of DFF funds |  |  | Draft DFF Training Manual
Malawi | LMH |  | Milestone 7: Quarterly review and feedback meetings for Community Health GC7 implementors Definition: Review meeting reports | BIRCH | 44052 |  | 2024-12-15 | 2024-12-15 | On track | There will be a need for reprogramming because two quarterly review meetings were planned but only one will take place in November 2024
Malawi | LMH | Review and revision of national scope of practice and training package for PHC workforce (including CHWs and their supervisors) | Milestone 1: Updated CHW standard operating procedures (SOPs). Definition: Comprehensive TA report with updated Standard Operating Procedures (SoP) for 5 cadres and clarified CHW roles (annexed) | BIRCH | 1803 |  | 2024-07-31 | 2024-10-31 | Delayed | This activity will be implemented as planned but in October with additional support of other partners through MoH. No need for reprogramming.
Malawi | LMH |  | Milestone 2: Orientation sessions/meetings on the updated JDs, SOPs and clarified roles conducted with the district councils Definition: Updated SoPs and Roles/ JD | BIRCH | 29050 |  | 2024-08-31 | 2024-09-30 | Delayed | This activity will be implemented as planned once milestone is effected in October.
Malawi | LMH |  | Milestone 3: CHWs trained/sensitized on the updated SOPs and revised/clarified roles (2025) Definition: Activity reports | BIRCH | 7762 |  | 2024-12-22 | 2025-03-31 | On track | This entire activity should be reprogrammed into 2025.
Malawi | LMH | Updated and costed national community health strategy | Milestone 1: NCHF costed implementation plan disseminated to Policymakers, MOH SMT, districts, donors and partners Definition: NCHF copies printed and Dissemination workshop conducted nationally and report submitted | BIRCH | 43473 |  | 2024-04-30 | 2024-06-30 | Complete | LMH provided supplementary support to the Ministry of Health (CHSS & DPPD) in disseminating the National Community Health Framework (NCHF) and the third Health Sector Strategic Plan (HSSP III) across four districts: Nsanje, Chikwawa, Rumphi, and Kasungu (See dissemination report).
Malawi | LMH |  | Milestone 2: The NCHF costed implementation plan reviewed and updated (to be implemented in 2025) Definition: The costed implementation plan updated, validated with National CHTWG and submitted | BIRCH | 4903 |  | 2024-12-31 | 2025-06-30 | Delayed | This activity will be reprogrammed to next year.
Mali | LMH | Amélioration ciblée de la qualité des soins et de la qualité dans les domaines prioritaires d'investissement des ASC | Milestone 1: Critères d'éligibilité pour la mise en place d'un mécanisme systématique de l'évaluation de l'éligibilité des CSCOM à la procédure d’accréditation digitalisés et disséminés Definition: Phase 1 : Rapport des ateliers de paramétrer des critères d’éligibilité des CSCom à la procédure d’accréditation (2024) Phase 2: Rapports des ateliers de digitalisation et de disséminations des critères de l'évaluation de l'éligibilité des CSCom à la procédure d'accréditation (2025) | BIRCH | 29406.3 |  | 2024-10-01 | 2024-11-30 | On track | TOR of the activity was developed. Will be completed by revised due date
Mali | LMH |  |  | BIRCH | 12690.53 |  | 2025-12-01 | 2025-12-01 | On track
Mali | LMH |  | Milestone 2: L'outil d’accréditation digitalisé Definition: Phase 1: l'outil d'accreditationent produits par le consultant (2024) Phase 2: Rapport de l'atelier de digitalisation de l'outils d'accréditation (2025) | BIRCH | 29700.01 |  | 2024-11-01 | 2024-11-01 | On track | Will be completed on due date
Mali | LMH |  |  | BIRCH | 20910.83 |  | 2025-12-01 | 2025-12-01 | On track
Mali | LMH |  | Milestone 3: Projet pilote d'offre de services intégrés pour booster la CPN dans les CSCom prioritaire du GC7 effective Definition: Phase 1:Plan de travail validé du consultant chargé d'appuyer la mise en œuvre du projet pilote, la version finale du projet pilote (2024) Phase 2: Rapport de suivi trimestriel du projet pilote d'offre de services intégrés dans les 65 CSCom du GC7 (2025) | BIRCH | 47131.15 |  | 2024-12-31 | 2024-12-31 | On track | Consultants recruited and have developped a technical note. Validation planned next week
Mali | LMH |  |  | BIRCH | 65983.61 |  | 2025-08-01 | 2025-08-01 | On track
Mali | LMH |  | Milestone 4: Référentiel pour accréditation des ASC élaboré Definition: Phase 1:Draft du referentiel d'accreditation des ASC élaboré par le consultant (2024) Phase 2: Rapport de l'atelier de validation du referentiel d'accreditation pour les ASC (2025) | BIRCH | 34952.25 |  | 2024-12-31 | 2024-12-31 | On track | TOR of the activity developed. Will be completed on due date
Mali | LMH |  |  | BIRCH | 6115.42 |  | 2025-12-31 | 2025-12-31 | On track
Mali | LMH |  | Milestone 5: Visite d'accréditation des ASC et des SD des sites d'interventions de Muso Definition: Rapports d'accreditation des ASC et SD des sites Muso (Hirimadio et Bankass) | BIRCH | 87596.07 |  | 2024-12-01 | 2025-06-30 | Complete | Rescheduled for 2025. Was already funded with Muso internal fund in 2024. BIRCH will then support activities in 2025.
Mali | LMH |  | Milestone 6: Visite d'accréditation des CSCom prioritaires du GC7 Definition: Phase 1: Rapport et attestation d'accreditation des CSCom prioritaires du GC7 du District de Bamako (2024) Phase 2: Rapport et attestation d'accreditation des CSCom prioritaires du GC7 des régions (2025) | BIRCH | 10092.5 |  | 2024-12-31 | 2025-03-31 | On track | This milestone has 3 activities. Pre requirements to be resolved: the list of health facilities on a validation process by health Minister Cabinet. For this reason, IP has requested to reshedule all the milestone in Q1 2025. OK for CFP
Mali | LMH |  |  | BIRCH | 111923.56 |  | 2025-12-01 | 2025-12-01 | On track
Mali | LMH | Rapports de suivi trimestriels sur la mise en œuvre des investissements dans la santé communautaire (sur la base de plans de mise en œuvre détaillés), y compris l'identification des goulots d'étranglement en matière de programmation et de capacité d'absorption, la résolution des problèmes et leur résolution dans les régions ciblées. | Milestone 1: Plan de travail semestriel du GC7 et du C19 en lien avec les activités de sante communautaire suivi et evalué Definition: Phase 1: Rapports de supervisions (avec niveau d'exécution des plan de travail semestriel 2024 des EMO et UMRSS pour les activités de santé communautaire) Phase 2: Rapports de supervisions (avec niveau d'exécution des plan de travail semestriel 2025 des EMO et UMRSS pour les activités de santé communautaire) | BIRCH | 98421.61 |  | 2024-11-01 | 2024-12-31 | On track | 2 supervisions were initially planned in 2024 but finally only is possible in 2024 due to the delay: 5 regions will be supervised. TDR & budgets in the process of validation for a supervison in 3 regions. Savings expected (50% of the amount)
Mali | LMH |  |  | BIRCH | 82248.97 |  | 2025-12-01 | 2025-12-01 | On track
Mali | LMH |  | Milestone 2: Revision de l'outils de supervision des supervisions dediés Definition: Phase 1: l'outil de supervision révisé, Rapport de l'atelier de revue de l'outil de supervision des superviseurs dédiés (2024) Phase 2: Rapport de l'atelier de paramettrage de l'outil revisé de la supervision des superviseurs dédiés (2025) | BIRCH | 45339.51 |  | 2024-12-31 | 2024-12-31 | Complete |  |  |  | CHWs dedicated supervision tool revision, 2024
Mali | LMH |  |  | BIRCH | 4633.98 |  | 2025-12-31 | 2025-12-31 | Complete | This milestone was completed in Q3 2024. The due date (december 2025) is more because of staff salaries in 2025. Awaiting supporting doccumentation |  |  | Report on the workshop to parameterize the CHWs dedicated revised supervision tool (2025)
Mali | LMH |  | Milestone 3: Tableau de bord des indicateurs SEC élaborés dans DHIS2 Definition: Rapport de l'atelier d'elaboration du tableau de bord des indicateurs clés du SEC dans le DHIS2 (2024, 2025) | BIRCH | 15019.52 |  | 2024-12-31 | 2024-12-31 | Complete
Mali | LMH |  |  | BIRCH | 12507.56 |  | 2025-12-31 | 2025-12-31 | On track
Mali | LMH | Répertoire national fonctionnel et géoréférencé des ASC hébergé dans un registre | Milestone 1: Interoperabilité effective entre DISC Mali, ASA Mali et DHIS2 Definition: Phase 1: Rapport des ateliers de finalisation de l'interoperabilité DISC Mali, ASA Mali et DHIS2 (2024) Phase 2: Rapport des ateliers de mise à niveau des administrateurs/Developpeurs de DISC Mali sur la maintenance du système (2025) | BIRCH | 66602.89 |  | 2024-10-01 | 2024-12-31 | On track | Activities will start next week. This milestone has 3 activities. 2 will be completed by October 2024 and IP has initially requested to reshedule the 3rd actvity in Q1 2025 but will finally complete it in Q4 2024. No need to reshedule
Mali | LMH |  |  | BIRCH | 43787.03 |  | 2025-12-01 | 2025-12-01 | On track
Mali | LMH |  | Milestone 2: Tableau de bord dynamique des ASC et SD fonctionnels dans DHIS2 Definition: Phase 1:Rapports d'ateliers de paramétrage de la liste maitresse géoréférencé hébergé dans DHIS2 (2024) Phase 2: Capture d'ecran du tableau de bord dynamique des Sites ASC du Mali (2025) | BIRCH | 11134.04 |  | 2024-10-31 | 2024-10-31 | Complete | Completed in August, awaiting for supporting documentation
Mali | LMH |  |  | BIRCH | 5803.39 |  | 2025-10-31 | 2025-10-31 | On track
Mali | LMH | Surveillance communautaire basée sur les événements (prestation à définir avec le ministère de la santé et les prestataires d'assistance technique SONAR+BIRCH dans les pays concernés) | Milestone 1: Paramétrage des formulaires SEBAC dans DISC Mali Definition: Phase 1: Rapport atelier de revue des formulaires SEBAC et CSU des ménages (2024) Phase 2: Rapport d'ateliers de paramétrage des formulaires SEBAC et CSU des menages dans DISC Mali (2025) | BIRCH | 15701.95 |  | 2024-12-01 | 2024-12-01 | Complete
Mali | LMH |  |  | BIRCH | 3285.87 |  | 2025-10-31 | 2025-10-31 | On track
Mali | LMH |  | Milestone 2: Test et validation des formulaires électroniques SEBAC Definition: Rapport d'ateliers de validation des formulaires SEBAC et CSU des menages | BIRCH | 30507.59 |  | 2025-12-31 | 2025-12-31 | On track
Mali | LMH |  | Milestone 3: Utilisateurs finaux formés sur les formulaires SEBAC Definition: Rapports des ateliers de formation des ASC sur les formulaires SEBAC de DISC Mali | BIRCH | 23300.53 |  | 2025-10-31 | 2025-10-31 | On track
Mali | LMH | Cartographie annuelle des investissements dans la santé communautaire par rapport à la stratégie nationale de santé communautaire (y compris l'intégration de la cartographie des investissements dans la santé communautaire dans les processus nationaux de cartographie des ressources et de suivi des dépenses). | Milestone: Carte des investissement de la santé Communautaire mise à jour chaque année Definition: Phase 1: Note conceptuelle de la cartographie des investissement en santé santé communautaire en 2024 Rapport de cartographie des investissement en santé santé communautaire validée, Rapport de validation de la cartographie des investissement annuels de la santé Communautaire.(2024, 2025) | SI | 35006.98 |  | 2024-10-31 | 2024-10-31 | On track
Mali | LMH |  |  | SI | 48699.7 |  | 2025-10-31 | 2025-10-31 | On track
Mali | LMH | Des plans opérationnels détaillés et coûtés pour la mise en œuvre de la stratégie nationale de santé communautaire, couvrant au moins les activités de CHW dans les subventions de fonds mondiaux pour faciliter la mise en œuvre des investissements CHW financés par les subventions du fonds mondial. | Milestone 1: Les drafts de plans opérationnels S1-2024 et 2025 élaborés avec la participations de toutes les régions du Mali Definition: Phase 1: Rapports de l'atelier preparatoire de revision des outils de planification (2024) Rapports de l'atelier d'élaboration des plans opérationnels avec liste de presence des participants (2025) | SI | 5047.86 |  | 2024-12-31 | 2024-12-31 | On track | Operational for 2024 cancelled. Only an operational for 2025 will be developed. A consultant evailable to support the process
Mali | LMH |  |  | SI | 50597.35 |  | 2025-12-31 | 2025-12-31 | On track
Mali | LMH |  | Milestone 2: Les versions finales des plans opérationnels S1-2024 et 2025 budgétisés du plan stratégique nationale 2021-2025 Definition: Versions finales des plans opérationnels budgétisés (2024, 2025) | SI | 547.48 |  | 2024-05-01 | 2024-12-31 | Delayed | A consultant recruited in other fund is available to support the process. He is currently undertaking a mi term review of the CH strategy and will support 2025 operational plan development
Mali | LMH |  |  | SI | 821.21 |  | 2025-01-31 | 2025-01-31 | On track
Mali | LMH | Évaluation annuelle de la maturité des systèmes des ASC | Milestone: Les plans d'action stratégiques issus des scores de notation de la matrice MEAP-ASC élaborés à la fin de chaque année Definition: Rapport final de l'évaluation de la maturité des systèmes des agents de santé communautaire (2024,2025). Rapport de l'atelier d'évaluation de la maturité des systèmes des agents de santé communautaire (2024, 2025) | SI | 27731.09 |  | 2024-12-01 | 2024-12-01 | On track
Mali | LMH |  |  | SI | 36048.47 |  | 2025-12-01 | 2025-12-01 | On track
Mali | LMH | Plan de financement durable à long terme (8-10 ans) et plan de mobilisation des ressources pour la santé communautaire / les agents de santé communautaire | Milestone 1: Dossier d'investissement de la santé communautaire validé Definition: Dossier d'investissement de la santé communautaire signé (2025) | SI | 52259.02 |  | 2025-10-31 | 2025-10-31 | On track
Mali | LMH |  |  | SI |  |  | 2025-10-31 | 2025-10-31 | On track
Mali | LMH |  | Milestone 2: Plan de financement durable élaboré et plan de mobilisation de ressource actualisé chaque année Definition: Plan de mobilisation de ressource annuel (domestique et externe) (2024, 2025) | SI | 5879.49 |  | 2024-10-01 | 2025-06-30 | Delayed | IP has requested to reshedule the milestone for 2025. OK CFP
Mali | LMH |  |  | SI | 10216.71 |  | 2025-12-01 | 2025-12-01 | On track
Mali | LMH | Stratégie nationale de santé communautaire actualisée et chiffrée | Milestone 1: Draft des axes stratégiques et résultats du nouveau plan stratégique nationale SEC 2026-2030 Definition: Rapport de l'atelier d'élaboration du nouveau plan stratégique SEC | SI | 7048.18 |  | 2024-10-01 | 2025-11-30 | Delayed | IP has requested to reshedule thise milestone for 2025. HR planned in 2024. The CH strategy development process will start in 2025. OK for CFP
Mali | LMH |  |  | SI | 76753.02 |  | 2025-06-01 | 2025-06-01 | On track
Mali | LMH |  | Milestone 2: Draft du nouveau plan stratégique national SEC budgétisé Definition: Rapport de l'atelier de budgétisation du nouveau plan stratégique SEC 2026-2030 | SI | 70390.75 |  | 2025-10-01 | 2025-10-01 | On track
Mali | LMH |  | Milestone 3: Rapport d'évaluation finale du plan stratégique national SEC Definition: Draft du nouveau plan strategique, Rapport de prestation du Consultant | SI | 18423.17 |  | 2025-10-01 | 2025-10-01 | On track
Mali | LMH |  | Milestone 4: Version finale du plan stratégique Definition: Version finale du nouveau plan stratégique SEC | SI | 17039.79 |  | 2025-10-31 | 2025-10-31 | On track
Mali | LMH |  | Milestone 5: Version validé par la ministre en charge de la santé du nouveau plan stratégique nationale SEC 2026-2030 Definition: Nouveau Plan stratégique national signé par la ministre en charge de la sante (2025) | SI | 34054.67 |  | 2025-12-01 | 2025-12-01 | On track
Senegal | LMH | Cartographie annuelle des investissements dans la santé communautaire par rapport à la stratégie nationale de santé communautaire (y compris l'intégration de la cartographie des investissements dans la santé communautaire dans les processus nationaux de cartographie des ressources et de suivi des dépenses) | Milestone: Réalisation de l'analyse documentaire à Dakar et projet de carte des ressources axée sur les investissements dans les services de santé communautaires dans 14 régions dont 2 jours par région la CSSP, Cellule d'Economie de la Santé, FAH, autres services MSAS, PTFs, etc Definition: Projet de carte des ressources axées sur les ASC et de plan d'intégration des RMET, fournis dans des formats spécifiques à BIRCH et adaptés au pays. | SI | 25930 |  | 2024-10-31 | 2024-10-31 | On track | Concept note on the process of validation by MoH. Tools development & validation planned in October Week 1 and will be followed by data collection by region
Senegal | LMH | Des plans opérationnels détaillés et chiffrés pour la mise en œuvre de la stratégie nationale de santé communautaire, couvrant au moins les activités de CHW dans les subventions de fonds mondiaux pour faciliter la mise en œuvre des investissements CHW financés par les subventions de fonds mondiaux. | Milestone 1:1-Lancement du processus d'élaboration des plans opérationnels détaillés et coutés pour la mise en oeuvre de la stratégie nationale de santé communautaire à Dakar par la CSSP, FAH en 7 jours Definition: Note conceptuelle | SI | 19779 |  | 2024-06-10 | 2024-09-30 | Delayed | FAH will finalize the Concept note by end of september
Senegal | LMH |  | Milestone 2: 2-Elaboration du projet de plan opérationnel annuel issu de la nouvelle stratégie nationale de santé communautaire (SNSC) 2025-2029 et consultation des parties prenantes et le finaliser au cours d'un atelier de 4 jours à Thiès avec 25 personnes Definition: Projet de plan opérationnel annuel issu de la SNSC soumis, Rapports de réunions, rapports d'engagement des parties prenantes, Plan opérationnel chiffré final validé et aligné sur les normes minimales | SI | 11325 |  | 2024-12-31 | 2025-01-01 | On track | Due to de delay on the new strategy development process, I anticipate it will be impossible to develop the operational plan in 2024. To push in Q1 2025
Senegal | LMH |  | Milestone 3: 3-Elaboration des plans opérationnels trimestriels détaillé et chiffré par districts & par régions chaque trimestre pendant 2 jours avec 15 participants à Dakar Definition: Plans opérationnels trimestriels détaillés et chiffrés par districts & par région | SI | 1516 |  | 2024-12-31 | 2025-02-28 | On track | same as above
Senegal | LMH | Évaluation annuelle de la maturité des systèmes des ASC | Milestone 1: 1. Lancement du processus d'évaluation de la maturité à Dakar par la CSSP pendant 5 jours Definition: Note conceptuelle de l'évaluation annuelle de la maturité du système de santé communautaire | SI | 14950 |  | 2024-11-08 | 2024-11-08 | On track | Concept note will be developed in october
Senegal | LMH |  | Milestone 2: 2.Consultation des parties prenantes et élaboration du projet d'évaluation de la maturité avec 40 participants à Diourbel pendant 4 jours Definition: Version préliminaire du rapport de l'évaluation de la maturité, rapport de l'atelier | SI | 16930 |  | 2024-11-22 | 2024-11-22 | On track
Senegal | LMH |  | Milestone 3: 3.Validation de l'évaluation finale de la maturité des ASC et diffusion du rapport avec 45 participants venant de DPRS,DAGE, DSME, CNLS,DRH,DP,DLM, SNEISS, DRS,Réseau National des ACS et PTFs pendant 1 jours Definition: Rapport final de l'évaluation validé de la maturité des ASC et rapport de l'atelier, diffusés à toutes les parties prenantes. | SI | 965 |  | 2024-12-12 | 2024-12-12 | On track
Senegal | LMH | Rapports de suivi trimestriels sur la mise en œuvre des investissements dans la santé communautaire (sur la base de plans de mise en œuvre détaillés), y compris l'identification des goulots d'étranglement en matière de programmation et de capacité d'absorption, la résolution des problèmes et leur résolution dans les régions ciblées. | Milestone 1: 1.Lancement du processus de suivi des investissements et des activités de santé communautaire Definition: Note conceptuelle | SI | 19779 |  | 2024-12-31 | 2024-12-31 | On track
Senegal | LMH |  | Milestone 2: 2-Organisation des réunions trimestrielles de bilan et de feedback Definition: Rapport d'examen trimestriel des réunions | SI | 20960 |  | 2024-10-31 | 2024-10-31 | On track | ToR to develop for the first review whorkshop (savings??? )
Senegal | LMH |  | Milestone 3: 3-Organisation de missions de supervision des Investissements/interventions communauttaires dans 2 régions chaque trimestre avec 8 agents pendant 5 jours par région Definition: Rapport de mission dans les régions (ces rapports permettront d'étoffer les rapports de suivis trimestriels des investissemnts) | SI | 13341 |  | 2024-10-31 | 2024-10-31 | On track | Discuss the relevance of pushing this in 2025 with regard to GC7 implementation delay
Senegal | LMH | Stratégie nationale de santé communautaire actualisée et chiffrée | Milestone 1: 1. Lancement du processus de la rédaction de la nouvelle stratégie nationale de santé communautaire à Dakar pendant 14 jours par les parties prénances (FAH, CSSP, Consultants, GTT, PTFs, etc.) Definition: Note conceptuelle | SI | 45768 |  | 2024-12-31 | 2024-12-31 | On track | More HR cost. A draft of rodamap for evaluation & strategy development submitted by FAH to CSSP. Will be revised during the 1st meeting of the technical committed, planned on 20 September
Senegal | LMH |  | Milestone 2: 2- Validation des résultats de l'évaluation du plan stratégique national de santé communautaire 2020-2024 et capitalisations des leçons et opportunités pour la rédaction du nouveau plan stratégique à Dakar pendant 2 jours par les parties prénantes (40 participants venant de DPRS,DSME,DP,DLM SNEISS,CNLS,DRH, Réseau National des ACS, DRS,PTFs, CSSP, FAH, Consultants, etc.) Definition: Rapport de validation des résultats de l'évaluation du plan stratégique national de santé communautaire 2020-2024 | SI | 9864 |  | 2024-06-30 | 2024-11-30 | Delayed | The recruitment of the 2 consultants is finalized, the technical committee set up and the 1st session to review and validate the roadmap developped by FAH
Senegal | LMH |  | Milestone 3: 4-Consolidation des differentes sessions des travaux de groupe à Dakar avec les parties prénantes (Consultants, FAH, GTT, PTFs) pendant 1 jour Definition: Rapport consolidé des différentes sessions des travaux de groupe | SI | 1893 |  | 2024-09-12 | 2024-11-30 | Delayed
Senegal | LMH |  | Milestone 4: 5-Rédaction des différentes sections de la nouvelle stratégie nationale de santé communautaire 2025-2029 à Dakar par le GTT avec les Consultants pendant 4 jours à Thiès Definition: Sections de la Stratégie nationale de santé communautaire 2025-2029 | SI | 15783 |  | 2024-09-19 | 2024-12-31 | Delayed
Senegal | LMH |  | Milestone 5: 6-Validation de la nouvelle stratégie nationale de santé communautaire 2025-2029 à Dakar avec 50 participants venant de DPRS,DAGE,DSME,DLM,DPSNEISS, CNLS,réseau national des ACS, DRS,PTFs, CSSP pendant 2 jours Definition: Plan stratégique national 2025-2029 validé | SI | 11951 |  | 2024-11-19 | 2024-12-31 | On track | Anticipate revised due date for december 2024 for technical validation. Political validation will happen in Q1 2025
Senegal | LMH |  | Milestone 6: 7-Diffusion dans les 14 régions avec le Niveau Central, ECR,ECD, PTFS pendant 3 jours par région de la nouvelle stratégie nationale 2025-2029 et Dissémination à Dakar avec100 participants venant des Directions et services du MSAS,DRS et autres secteurs,Réseau National des ACS et PTFs pendant 1 jour Definition: Rapport de Diffusion et Rapports de Dissémination de la stratégique nationale 2025-2029 | SI | 19965 |  | 2024-12-19 | 2025-03-31 | On track | Anticipate that this is not feasible in 2024, with regards to the delay: 4 remaining for to evaluate and developed the new strategy.
Sierra Leone | LMH | Annual assessment of CHW systems maturity | Milestone 1: Plan and conduct January 2024 CHW systems maturity assessment Definition: CHW Maturity Assessment report | BIRCH | 12360 |  | 2024-01-31 | 2024-01-31 | Complete |  |  |  | Maturity Assessment Report
Sierra Leone | LMH | Annual assessment of CHW systems maturity | Milestone 2: Disseminate Phase 1 CHW systems maturity assessment findings and action plan (meetings with MOH and other stakeholders) Definition: Consolidated dissemination meeting reports | BIRCH | 5821.3 |  | 2024-05-30 | 2024-08-30 | Complete | Maturity assessment findings was one of three CHW assessment data sources disesminated at a national event on August 8-9 in Freetown. There is ongoing engagement with the MOH (CHW Hub and DPPI) to review recommendations and action plan with key stakeholders to priortize and implement data-driven quality improvements. |  |  | National Dissemination Slide Deck
Sierra Leone | LMH | Annual mapping of investments in community health against the national community health strategy (including integration of community health investment mapping into national Resource Mapping and Expenditure Tracking processes) | Milestone 1: Cross-referenced 2024-2025 costed operational plan with the 2021-2025 CHW Strategy. Definition: Comprehensive resources/donor mapping document | BIRCH | 7212.51 |  | 2024-09-30 | 2024-10-31 | Delayed | - Part of this work is incorporated into the CHW Operational Plan development as most of the information needed for resource/donor mapping would be collected whilst developing the costed operational plan. - The Ops Plan template is being carefully developed to gather such information - Following, a resource/donor mapping template would then be populated. No reprogramming is required.
Sierra Leone | LMH |  | Milestone 2: Determine potential 2025 RMET milestone based on 2024 progress and learnings Definition: Resource mapping and expenditure verification report | BIRCH | 5475.51 |  | 2024-09-30 | 2024-09-30 | On track | No reprogramming is required. This activity will be completed in October 2024.
Sierra Leone | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone 1: Review activities included in CHW strategy (2021-2025) and break down to sufficient detail as needed for operational planning Definition: Plan of action detailing scope of the operational plan development process | BIRCH | 4188.89 |  | 2024-05-16 | 2024-10-31 | Delayed | A draft Operational plan template has been developed and pre-populated with strategic objectives and activities from the the NCHWP Strategy (2021-2025). No reprogramming is required.
Sierra Leone | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone 2: Develop draft operational plan (reflect strategic priorities as laid out in the CHW strategy (2021-2025) Definition: Draft operational plan | BIRCH | 5184.17 |  | 2024-06-15 | 2024-08-30 | Delayed | - A draft pre-populated Operational plan template ready for stakeholder consultation - CHW Hub to make a final review ahead of stakeholder workshop. No reprogramming required. This activity will be completed in September 2024
Sierra Leone | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone 3: Stakeholder consultation to review draft operational plan (include disease programs, DHMT reps, partners, etc.) Definition: Meeting notes from stakeholder consultations | BIRCH | 4580.2 |  | 2024-06-30 | 2024-09-30 | Delayed | Stakeholder consultation (workshop) to develop NCHWP operational plan is scheduled for Sept. 17-18. This activity is on course, no reprogramming is required. - TWG members identified and approved by MOH - Pre-work is ongoing - documentation, stakeholder follow up
Sierra Leone | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone 4: Finalize costed operational plan (incorporates all costing data of strategic priorities) Definition: Finalized and validated operational plan | BIRCH | 6125.94 |  | 2024-07-31 | 2024-10-31 | Delayed | This activity is dependent on stakeholder consultation happening in September and will be finalized in October 2024.
Sierra Leone | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone 5: Launch/roll out (2024-2025) operational plan with national and subnational stakeholders (DHMT, partners, disease programs, other MOH units) Definition: Workshop report | BIRCH | 4844.11 |  | 2024-08-15 | 2024-10-30 | Delayed | No reprogramming is required. This activity will be completed in October 2024.
Sierra Leone | LMH | Functional national georeferenced CHW master list hosted in a registry | Milestone 1: CHW Master List Needs Assessment Definition: Copy of CHW masterlist detailing data/information gaps | BIRCH | 40450.19 |  | 2024-09-30 | 2024-09-30 | On track | - Validation workshop of the CHW microplanning data to inform the master list was done. Ongoing work by MOH and LMH to consolidate all inputs from the workshop into a draft masterlist template - Interviews for geo mapping consultant in it final stages. No reprogramming is required | 31st July 2024
Sierra Leone | LMH | Functional national georeferenced CHW master list hosted in a registry | Milestone 2: CHW Master List Tool Piloting Definition: Geomapping data collection tool - template and pretested; tool pretesting report | BIRCH | 8840.46 |  | 2024-07-31 | 2024-10-31 | Delayed | Same as above - No reprograming is required
Sierra Leone | LMH | Functional national georeferenced CHW master list hosted in a registry | Milestone 3: CHW Masterlist Implementation Prep Definition: Enumerators training report | BIRCH | 51012.72 |  | 2024-08-31 | 2024-11-30 | Delayed | This activity is on course to be implemented in November after the above milestones. No reprogramming is required
Sierra Leone | LMH | Functional national georeferenced CHW master list hosted in a registry | Milestone 4: Implementation of geomapping Definition: Comprehensive report; electronic copy of analysed CHW data | BIRCH | 71784.46 |  | 2024-09-30 | 2024-12-31 | On track | Same as above - This activity is on course to be implemented in November after the above milestones. No reprogramming is required
Sierra Leone | LMH | Functional national georeferenced CHW master list hosted in a registry | Milestone 5: Integration of geo data into CHW Master List + QI of other data fields Definition: Comprehensive CHW masterlist | BIRCH | 5274.47 |  | 2024-11-30 | 2024-12-31 | On track | Same as above - This activity is on course to be implemented in December after the above milestones. No reprogramming is required
Sierra Leone | LMH | Functional national georeferenced CHW master list hosted in a registry | Milestone 6: Develop CHW Masterlist SOP Definition: SOP for use of CHW masterlist | BIRCH | 3349.15 |  | 2024-10-31 | 2025-03-31 | On track | This entire activity should be reprogramed to first quarter 2025.
Sierra Leone | LMH | Functional national georeferenced CHW master list hosted in a registry | Milestone 7: CHW Master List & SOP Dissemination Definition: Masterlist Disseminatin report | BIRCH | 1957.65 |  | 2024-10-31 | 2025-03-31 | On track | This entire activity should be reprogramed to first quarter 2025.
Sierra Leone | LMH | Quarterly monitoring reports on implementation of community health investments (based on Detailed implementation plans) including identification of programmatic and absorption bottlenecks, problem solving and resolution in targeted regions | Milestone: Quarterly monitoring and feedback on implementation of community health investments Definition: Meeting/monitoring reports and progress tracker | BIRCH | 51532.2 |  | 2024-11-30 | 2024-11-30 | On track | BIRCH team met with CCM to: - update CCM on BIRCH - discuss milestone (monitoring GF CH investments) - determine CCM's roles - support in convening meetings with GF PRs/IP Agreed actions: - LMH to meet with leadership teams of PRs (MOH and WVISL) - with CCM in attendance - Director PHC setting up meeting with MOH leadership - LMH setting up meeting WVISL . This entire activity will need reprogramming to just 1 meeting out of the two planned for this period.
Sierra Leone | LMH | Review and revision of national scope of practice and training package for PHC workforce (including CHWs and their supervisors) | Milestone 1: Urban CHWs - SOW/policy addendum developed (via Technical Working Group including HIV/TB) Definition: SOW for urban CHW recruitment and training; final copy of policy addendum for urban CHWs; stakeholder engagement reports | BIRCH | 9055.12 |  | 2024-06-30 | 2024-12-31 | Delayed | CHWs were trained in March 2024 when the BIRCH work plan was still being finalized, this deliverable is not due until December, 2024. This activity will commence in October 2024. No need for reprogramming
Sierra Leone | LMH | Review and revision of national scope of practice and training package for PHC workforce (including CHWs and their supervisors) | Milestone 2: CHW Recruitment & Pre-service CHW training package review- Training Quality Improvement validation and stakeholder (national & subnational) feedback integration Definition: Revised and updated training package - all modules | BIRCH | 2824.09 |  | 2024-06-30 | 2024-11-30 | Delayed | MOH/CHW Hub is seeking funds to cover CHW training, until then milestone can possibly be deproritized and moved to Yr2. This activity can still be implemented in November 2024 with no need for reprogramming.
Sierra Leone | LMH | Review and revision of national scope of practice and training package for PHC workforce (including CHWs and their supervisors) | Milestone 3: CHW Pre-service training (prepare for quality training) Definition: Training scope/plan - comprehensive list of CHWs, training sites, trainers, training budget, etc. | BIRCH | 86400.12 |  | 2024-08-31 | 2025-03-31 | Delayed | This entire activity can potentially be reprogrammed to 2025 if no funding is immediately made available to train 1000 urban CHWs by the government.
Sierra Leone | LMH | Review and revision of national scope of practice and training package for PHC workforce (including CHWs and their supervisors) | Milestone 4: Develop CHW In-Service Training SOP & Materials- scoping with competency analysis & stakeholder engagement Definition: Finalized SOP | BIRCH | 2978.72 |  | 2024-08-31 | 2024-12-31 | Delayed | same as above
Sierra Leone | LMH | Targeted Quality of Care/Quality Improvement rolled out in priority areas of CHW investment | Milestone 1: QI M&E- Develop M&E framework Definition: M&E framework draft; summary report of development activities | BIRCH | 16137 |  | 2024-09-30 | 2024-10-30 | On track | - confirming final list of TWG members (Integrated programs M&E staff, CHW Hub, DPPI, partners) - Ongoing engagements and preliminary work with MOH/CHW Hub M&E officers providing clarity on the requirements and determining existing M&E frameworks - Identifying existing data sources and processes along with their quality (e.g. CHIS, Community Scorecard, CHW Supervision, etc.). No need for reprogramming, this activity will be implemented as planned.
Sierra Leone | LMH | Targeted Quality of Care/Quality Improvement rolled out in priority areas of CHW investment | Milestone 2: QI M&E- Develop M&E SOPs (M&E framework, data review, etc. SOPs) Definition: M&E SOPs | BIRCH | 4994.34 |  | 2024-11-15 | 2024-11-15 | On track | No need for reprogramming, this activity will be implemented as planned.
Sierra Leone | LMH | Targeted Quality of Care/Quality Improvement rolled out in priority areas of CHW investment | Milestone 3: QI M&E- Disseminate M&E framework and SOPs Definition: Workshop report | BIRCH | 6507.65 |  | 2024-12-12 | 2024-12-12 | On track | No need for reprogramming, this activity will be implemented as planned.
Sierra Leone | LMH | Targeted Quality of Care/Quality Improvement rolled out in priority areas of CHW investment | Milestone 4: QI- Supply Chain: Conduct CHW commodity Supply Chain SOP and quantification, ordering, distribution tool (scoping & key stakeholder engagement) Definition: Comprehensive list of supply chain documents - guidelines, SOPs, TORs | BIRCH | 8666.84 |  | 2024-10-31 | 2024-10-31 | On track | Ongoing preliminary work to review available national SOPs and other stratgic documents and initiating CHW Hub engagements with RHFP forecast and SC TWG. No need for reprogramming
Sierra Leone | LMH | Targeted Quality of Care/Quality Improvement rolled out in priority areas of CHW investment | Milestone 5: QI- Leadership & Governance: Develop NCHWP Management SOP (scoping & key stakeholder engagement) Definition: Comprehensive list of lNCHWP leadership and management documents - guidelines, SOPs, TORs | BIRCH | 3822 |  | 2024-09-30 | 2024-12-31 | Delayed | This activity will be implemented as planned in November 2024. No need for reprogramming.
Sierra Leone | LMH | Targeted Quality of Care/Quality Improvement rolled out in priority areas of CHW investment | Milestone 6: QI- Leadership & Governance: Disseminate and rollout NCHWP Management SOP (National and subnational MOH and partners stakeholders) Definition: Printed and electronic copies of signed-off NCHWP leadership and management SOP | BIRCH | 4512.05 |  | 2024-10-24 | March 31st 2025 | On track | Given that these ouptputs are likely to be completed in December 2024, the sign off and printing is likely to happen in 2025. This activity will be required to be reprogramed to first quarter 2025
Sierra Leone | LMH | Targeted Quality of Care/Quality Improvement rolled out in priority areas of CHW investment | Milestone 7: QI- Leadership & Governance: 2 bi-annual coordination and management meetings for NCHWP managers conducted Definition: Consolidated minutes/reports from stakeholder meetings | BIRCH | 11852.34 |  | 2024-11-15 | March 31st 2025 | On track | These bi-annual meetings are only likely to take place in 2025 first quarter hence the reprogramming.
Sierra Leone | LMH | Targeted Quality of Care/Quality Improvement rolled out in priority areas of CHW investment | Milestone 8: QI- Leadership & Governance: Strengthen subnational coordination and management of the NCHWP (CHW focal capacity and reflection meetings) Definition: Training slides and reports | BIRCH | 33993.2 |  | 2024-11-15 | 2025-03-31 | On track | Since this activity is dependent on the two milestones above, it should be reprogrammed to first quarter 2025.
Sierra Leone | LMH | Targeted Quality of Care/Quality Improvement rolled out in priority areas of CHW investment | Milestone 9: QI HRH Supervision: Develop referral SOP between CHW & PHU to prevent loss to care Definition: Approved and signed off SOP | BIRCH | 8180.53 |  | 2024-08-31 | 2024-09-30 | Delayed | We deprioritized this in August in order to focus on the operational plan milestone. We plan to start work on this in September. No need for reprogramming since this activity is on course.
Sierra Leone | LMH | Targeted Quality of Care/Quality Improvement rolled out in priority areas of CHW investment | Milestone 10: QI HRH Supervision: Disseminate referral SOP to DHMTs and PHUs Definition: Availability of SOPs in DHMTs and PHUs | BIRCH | 575 |  | 2024-10-31 | 2024-09-30 | On track | same as milestone 1 - no need for reprogramming
Sierra Leone | LMH | Targeted Quality of Care/Quality Improvement rolled out in priority areas of CHW investment | Milestone 11: QI HRH Supervision: Orientate PHUs on referral SOP Definition: Slide deck, minutes, reports | BIRCH | 8225.34 |  | 2024-10-31 | 2024-10-31 | On track | same as milestone 1 and 2 - no need for reprogramming
Sierra Leone | LMH | Targeted Quality of Care/Quality Improvement rolled out in priority areas of CHW investment | Milestone 12: QI HRH Supervision: Conduct joint HRH and DPHC/CHW Hub district engagement to determine CHW/HRH issues Definition: Reports of joint/site visits | BIRCH | 7242.09 |  | 2024-10-31 | 2024-11-30 | On track | same as milestones 1, 2, and 3 - no need for reprogramming
Uganda | LMH | Annual mapping of investments in community health against the national community health strategy (including integration of community health investment mapping into national Resource Mapping and Expenditure Tracking processes) | Milestone: Resource mapping & expenditure Dashboard Definition: Draft a CHW focused resource map, taking into account minimum standards Expenditure tracking platform/dashboard | BIRCH | 14493 |  | 2025-09-30 | 2025-09-30 | On track | Developed mapping tool under refinement. (HERE) Currently the team is working on incorporating comments from AFF and the MOH with planned dissemination of the tool planned for the week starting September 9th
Uganda | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone: Operational plan for the implementation of the updated CHEW strategy Definition: Approved CHEWS operational plan | BIRCH | 32707 |  | 2025-03-30 | 2025-03-30 | On track
Uganda | LMH | Long-term (8-10 year) sustainable financing plan and resource mobilization plan for community health / community health workers | Milestone: Final sustainable financing plan Definition: Outline of sustainable financing plan Draft sustainable financing plan Final validated sustainable financing plan | BIRCH | 30974 |  | 2025-10-31 | 2025-10-31 | On track
Uganda | LMH | Quarterly monitoring reports on implementation of community health investments (based on Detailed implementation plans) including identification of programmatic and absorption bottlenecks, problem solving and resolution in targeted regions | Milestone: Quarterly monitoring reports Definition: Quarterly operational plan (2024, 2025) Quarterly review report (2024, 2025) An action plan highlighting key issues to be addressed, timelines and responsible party (2024, 2025) | BIRCH | 3814 |  | 2024-10-31 | 2024-10-31 | On track | Ongoing discussions around the scope of this exercise and the need to avoid duplicating the existing grant management processes aimed at following up on the progress of community health activities
Uganda | LMH |  |  | BIRCH | 4002 |  | 2025-10-29 | 2025-10-29 | On track
Uganda | LMH | Targeted Quality of Care/Quality Improvement rolled out in priority areas of CHW investment | Milestone 1: CHEW Workflows & eCHIS hierarchy modification Definition: CHEWs mind maps & Links to the designed tools, Evidence of addition of parish level heirachy | BIRCH | 36335 |  | 2024-11-30 | 2024-11-30 | On track | The preparatory work has commenced where the team is work in partnership with MEDIC on: a) Defination of Prioritized needs, refined the problem, and defined requirements (synthesis); Document and select user roles; Review existing product capabilities; Reference best practices; Discussions with key stakeholders) b) Ideation: Brainstorm options to meet user needs (draft potential solutions). Consider multiple ways of solving the design challenge. Draw workflow sketches
Uganda | LMH |  | Milestone 2: CHEWs Workflow and Analytics Co-creation Workshop Definition: Report from the CHEWs Workflow (2024) and Analytics Co-creation Workshop (2025) | BIRCH | 23716 |  | 2024-12-31 | 2024-12-31 | On track | The preparatory work has commenced where the team is working in partnership with MEDIC on: a) Defination of Prioritized needs, refined the problem, and defined requirements (synthesis); Document and select user roles; Review existing product capabilities; Reference best practices; Discussions with key stakeholders) b) Ideation: Brainstorm options to meet user needs (draft potential solutions). Consider multiple ways of solving the design challenge. Draw workflow sketches
Uganda | LMH |  |  | BIRCH | 22826 |  | 2025-03-30 | 2025-03-30 | On track | Dependent on completion of milestone 1
Uganda | LMH |  | Milestone 3: eCHIS Version Upgrade Definition: upgraded eCHIS application (Current version is 4.2.4) | BIRCH | 5521 |  | 2025-03-30 | 2025-03-30 | On track | Upgrade process initiated stakeholder consultation held through the MoH working groups, plan developed, successfully tested with the dev instance, Ready for the update
Uganda | LMH | Updated and costed national community health strategy | Milestone 1: Resources availed to coordinate CHEW strategy implementation Definition: TORs developed (2024) Activity reports (2025) | BIRCH | 23221 |  | 2024-12-31 | 2024-12-31 | On track | The resource (M&E advisor) was identified, recruited, and orientated on the project aim, and is currently working.
Uganda | LMH |  |  | BIRCH | 43226 |  | 2025-12-31 | 2025-12-31 | On track
Uganda | LMH |  | Milestone 2: Updated and costed Community Extension Workers (CHEWS) Strategy Definition: Validated, updated and costed community Extension Workers strategy | BIRCH | 33110 |  | 2024-12-31 | 2024-12-31 | On track | Definition of SOW finalized Consultant Identification done in partneship with MoH and curently there are two finalists Final selection to be through a presentation on the SOW and due diligence.
Uganda | LMH |  | Milestone 3: Village Health Team (VHT) Revitalization Strategy Definition: Draft a VHT Revitalization Strategy | BIRCH | 24627 |  | 2025-12-30 | 2025-12-30 | On track | As above
Zambia | LMH | Functional national georeferenced CHW master list hosted in a registry | Milestone 1: Technical Assistant concept note developed Definition: TA visit conducted in the implementation of georeferenced CHW master list | BIRCH | 10778 |  | 2024-04-30 | 2024-10-11 | Delayed | TA was delayed because we wanted migration of ML to HRIS and for the team to develop SoP to guide TA delivery. TA now planned for the 28th of September targeting 48 districts to be completed by first week of October 2024.
Zambia | LMH |  | Milestone 2: National Georeference CHW Master list user manual developed Definition: Training report for end-users/stakeholders on how to access and use the registry | BIRCH | 13872 |  | 2024-08-30 | 2024-09-30 | Delayed | This was delayed because it was dependent on the availability of the user Manual (SoP) which was developed this Q3. The training plan is currently being developed and will be shared shortly. This activity will commence on 22nd September for 5 days involving other stakeholders (like pepfar etc) and some sellected districts.
Zambia | LMH | Capacity assessment of relevant MOH directorates (CH/HRH) and tailored capacity building plan developed and implemented | Milestone: Capacity built for CH/HRH in Gender transformative leadership for Community Health (CHW, Structures, Systems) Definition: Capacity building report for CH/HRH in Gender transformative leadership for Community Health(CHW, Structures, systems) | BIRCH | 186777 |  | 2024-11-30 | 2024-11-30 | On track | This component is dependent on CBV recruitment and orientation under GC7 (Targeting 12). FAH will roll out this training when the CH integrated service package is being delivered in September. We will have to check on CBV recruitment progress by PRs. First the training will cover MoH, PHO and DHO then cascade to CBVs starting second week of october with support of Dr. Thenjiwe. Preparatory work has already commenced. (We need to reprogram part of these funds to cover a 2024 Maturity Assessment and 2025 CBV cascade training). we need support of finance team to support with this bit.
Zambia | LMH | Legal framework for CHWs defined | Milestone: Dissemination of legal frameworks for CHWs Definition: Dissemination meeting report | BIRCH | 7906 |  | 2024-07-30 | 2024-09-30 | Delayed | National level dissemination (Share the report) was done and sub-national is yet to happen in some districts. Dissemination plan not yet done but we're targeting 20 districts and timelines to be shared. The dissemination plan is now developed and letter to districts has already been sent. This milestone will be completed in October 2024.
Zambia | LMH | Targeted Quality of Care/Quality Improvement rolled out in priority areas of CHW investment | Milestone 1: CHW Mentorship, SQA,and Supervisory Tools Developed Definition: Validated CHW Mentorship,SQA and Supervisory tools | BIRCH | 30419 |  | 2024-07-30 | 2024-10-31 | On track | First drafts were developed in May and validation including pre-testing to happen in August. Validation has now happened pending pre-testing of the tools in October 2024. |  |  | Draft CHW Supervision SOP and Tools in place https://drive.google.com/drive/folders/1WETLYjN7io1LfbslUMLcdRnRVYaLSopV?usp=sharing
Zambia | LMH |  | Milestone 2: TQoC/QI roll out concept and plan developed Definition: Community quality improvement collaborative meeting report | BIRCH | 10505 |  | 2024-10-30 | 2024-11-30 | On track | Dependent on milestone one completion - this activity will be completed in November 2024
Zambia | LMH | Community event-based surveillance (deliverable to be defined with MOH and SONAR+BIRCH TA providers in applicable countries) | Milestone: Light -Touch collaboration with SONAR to align maturity model tools Definition: TA report on CBV and CHAs community based surveillance activities during routine field visits | BIRCH | 12702 |  | 2024-09-30 | 2024-10-31 | On track | Concept Note on this work is already developed. The agreed approach is that Specific districts prone to outbreaks will be targeted (10) by MoH and ZNPHI in September 2024. A checklist on specific surveillance issues affecting communities (including Mpox, COVID, Cholera) has now been developed. This will be used to build capacity of CBVs to report outbreaks. ZNPHI & RESOLVE need to jointly plan with MoH to kick off this activity. (FAH to revert sooner on planning arrangements). This activity will be completed by the planned dates.
Zambia | LMH | Integrated HRH/CHW Strategic Plan | Milestone: Concept note developed Definition: Developed intergrated HRH/CHW strategic plan | BIRCH | 20528 |  | 2024-07-30 | 2024-10-31 | Delayed | Sub-committee was formed during HRH TWG to review HRH strategy. Task force on transitioning and sustainabilty was tasked to develop the CN on how to review the HRH strategy. September was the new targeted date of completion but changed to 31st October due to competing MoH priorities in September.
Zambia | LMH | Updated and costed national community health strategy | Milestone: Dissemination plan and roadmap developed Definition: Dissemination report | SI | 4410 |  | 2024-06-30 | 2024-06-30 | Complete
Zambia | LMH | National harmonized payscale for CHWs | Milestone 1: Dissemination plan and roadmap developed Definition: Dissemination report | SI | 12869 |  | 2024-06-30 | 2024-06-30 | Complete
Zambia | LMH | Quarterly monitoring reports on implementation of community health investments (based on Detailed implementation plans) including identification of programmatic and absorption bottlenecks, problem solving and resolution in targeted regions | Milestone 1: Quarterly monitoring report developed Definition: Quarterly monitoring reports | SI | 140475 |  | 2024-12-30 | 2024-12-30 | On track | This activity will commence in Q 3 – budget savings for the first 2 quarters and re-allocation to be discussed. There is postential of Cost-sharing on these meetings with PRs. From 17th - 27th September PHO and DHOs will host first BIRCH supported review meetings focused on CH investments. Template already shared with teams. Only two quarterly review meetings will be implemented this year and the rest will be reprogrammed.
Zambia | LMH | Review and revision of national scope of practice and training package for PHC workforce (including CHWs and their supervisors) | Milestone 1: Reviewed CHW Guidelines Definition: CHW guidelines revised | SI | 20126 |  | 2024-07-30 | 2024-10-31 | Delayed | Revised Draft NHC guidelines have been developed developed to inform the development of CHW Guidelines. NHC guidelines are now going to be validated for coherence end of September and therefater revise the CHW guidelines by October 2024.
Zambia | LMH |  | Milestone 2: Develop the concept note for the CHA Peer-to-Peer Supervision guidelines and tools Definition: Development of CHA peer-to-peer supervision guidelines and tools | SI | 5198 |  | 2024-07-30 | 2024-11-30 | Delayed | This activity is on hold pending finalization of NHC/CHW guidelines/TQC doc. The next steps we await for the finalisation of the CHW revised guidelines in October 2024 and thereafter complete the CHA tools in November.
Zambia | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone: Concept note developed Definition: Monitoring report of operational plan implementation | SI | 719 |  | 2024-10-30 | 2024-10-30 | On track | This is dependent on the finalization of the Updated and costed national community health strategy. The op plan is now developed and the monitoring of the same is now happening at MoH central level.
Zambia | LMH | Annual assessment of CHW systems maturity | Milestone: Dissemination plan developed and key stakeholders identified through TWGs Definition: Dissemination report of the annual assessment of CHW systems maturity | SI | 25877 |  | 2024-12-30 | 2024-12-30 | On track | Maturity Assessment Report is now finalized and ready for dissemination in the first week of October 2024.
Zambia | LMH | Long-term (8-10 year) sustainable financing plan and resource mobilization plan for community health / community health workers | Milestone: Long-Term Sustainable Financing plan and resource mobilization plan developed Definition: Dissemination meeting report of the longterm sustainable financing plan and resource mobilization plan for community Health/CHW | SI | 28129 |  | 2024-09-30 | 2024-12-31 | Delayed | Delayed due to workplan development. Discussions with UNICEF, AfCDC, MUSO, and other partners are underway to develop the roadmap and Concept Note. Right now MoH need to disseminate the Res Mob plan during the National CH symposium in Zambia in December. Consultation will happen in October 2024 on LT to develop the roadmap for the same. This activity will commence in Q4 2024 and complete in Q1 2025.
Zambia | LMH | Annual mapping of investments in community health against the national community health strategy (including integration of community health investment mapping into national Resource Mapping and Expenditure Tracking processes) | Milestone: Develop standardised Framework Definition: Framework Developed and operational plan | SI | 15806 |  | 2024-12-30 | 2024-12-30 | Complete | A CN is already developed and a meeting is planned for the first week of September to develop the framework. This activity is now complete.
Zimbabwe | LMH | Annual assessment of CHW systems maturity | Milestone 1: Working with MOHCC, checklist for an annual assessment of the VHW systems maturity developed Definition: Annual VHW maturity assesment checklist developed and submitted | BIRCH | 13487 |  | 2024-08-31 | 2024-09-30 | Delayed
Zimbabwe | LMH | Annual assessment of CHW systems maturity | Milestone 2: Working with national level MOHCC, conduct annual assessment of the VHW systems maturity Definition: Annual VHW maturity assesment report submitted, one for 2024, and the other for 2025 | BIRCH | 11821 |  | 2024-09-30 | 2024-09-30 | On track
Zimbabwe | LMH | Annual assessment of CHW systems maturity |  | BIRCH | 14029 |  | 2025-09-30 | 2025-09-30 | On track
Zimbabwe | LMH | Annual mapping of investments in community health against the national community health strategy (including integration of community health investment mapping into national Resource Mapping and Expenditure Tracking processes) | Milestone 1: Work with the MOHCC and develop the VHW investment resource mapping tool Definition: Revised resource mapping data collection tool for community health interventions submitted | BIRCH | 13487 |  | 2024-09-30 | 2024-09-30 | On track
Zimbabwe | LMH | Annual mapping of investments in community health against the national community health strategy (including integration of community health investment mapping into national Resource Mapping and Expenditure Tracking processes) | Milestone 2: Work with MOHCC and collect VHW investment resource mapping data across the Global Fund Grants (HIV/TB/Malaria/C19RM) and other partner investments for community health and VHWs Definition: VHW investment mapping resource data tool populated and submitted | BIRCH | 15327 |  | 2024-10-31 | 2024-10-31 | On track
Zimbabwe | LMH | Annual mapping of investments in community health against the national community health strategy (including integration of community health investment mapping into national Resource Mapping and Expenditure Tracking processes) | Milestone 3: Resource mapping and investment data analyzed and synthesized in annual investment mapping report, with outputs used to inform operational planning, partner coordination, TWG meetings, etc. Definition: Annual investment mapping report submitted and analyses developed for overall community health and VHW investments, One for 2024 and the other for 2025. | BIRCH | 14146 |  | 2024-12-31 | 2024-12-31 | On track
Zimbabwe | LMH | Annual mapping of investments in community health against the national community health strategy (including integration of community health investment mapping into national Resource Mapping and Expenditure Tracking processes) | Milestone 3: Resource mapping and investment data analyzed and synthesized in annual investment mapping report, with outputs used to inform operational planning, partner coordination, TWG meetings, etc. Definition: Annual investment mapping report submitted and analyses developed for overall community health and VHW investments, One for 2024 and the other for 2025. | BIRCH | 17511 |  | 2025-12-31 | 2025-12-31 | On track
Zimbabwe | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone 1: Through stakeholder engagement and analysis, and working with MOHCC PCU, DNS and UNDP, Malaria, TB and HIV teams, consolidated annual operational plans for GF investments in community health and VHWs developed Definition: Focused annual operational plans (2024, 2025) for VHW program developed that leverage and streamline GF investments across its multiple grants, implemented in financial year 2024/2025 and financial year 2025/2026 | BIRCH | 11821 |  | 2024-09-30 | 2024-09-30 | On track
Zimbabwe | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. |  | BIRCH | 14029 |  | 2025-10-31 | 2025-10-31 | On track
Zimbabwe | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. | Milestone 2: Through stakeholder engagement, CHAI will consolidate the annual operational plan for GF investments with other VHW investments identified during the mapping process Definition:The output will be a consolidated annual plan that includes other investments on top of the GF funded activities, one for 2024 and the other for 2025. | BIRCH | 5334 |  | 2024-12-01 | 2024-12-01 | On track
Zimbabwe | LMH | Detailed and costed operational plans for implementation of the national community health strategy, covering at minimum the CHW activities in Global Fund grants to facilitate implementation of CHW investments funded by Global Fund grants. |  | BIRCH | 8153 |  | 2025-12-01 | 2025-12-01 | On track
Zimbabwe | LMH | Functional national georeferenced CHW master list hosted in a registry | Milestone 1: CHWML data compiled in single excel file, analyzed for quality, and cleaned Definition: Final Excel-based dataset (CHWML) submitted | BIRCH | 13487 |  | 2024-09-28 | 2024-09-28 | On track
Zimbabwe | LMH | Functional national georeferenced CHW master list hosted in a registry | Milestone 2: Conduct training of provincial heads on the CHWML data collection tool/ process Definition: Brief report submitted documenting the trainings conducted for provincial leads on the CHWML data collection tool | BIRCH | 18432 |  | 2024-08-30 | 2024-10-31 | Delayed
Zimbabwe | LMH | Functional national georeferenced CHW master list hosted in a registry | Milestone 3: Protocol developed for how, when and by whom the Excel-based master list will be updated Definition: Protocol / SOP for updating the CHWML submitted | BIRCH | 13487 |  | 2025-03-30 | 2025-03-30 | On track
Zimbabwe | LMH | Functional national georeferenced CHW master list hosted in a registry | Milestone 4: Working with MOHCC, a data collection tool for the CHWML (that will collect additional fields of VHW demographic data) will be developed, including with measures for data quality Definition: VHW master list data collection tool/ developed and submitted, with recommended process for data collection articulated in brief accompanying concept note | BIRCH | 13487 |  | 2024-07-31 | 2024-10-31 | Delayed
Zimbabwe | LMH | Quarterly monitoring reports on implementation of community health investments (based on Detailed implementation plans) including identification of programmatic and absorption bottlenecks, problem solving and resolution in targeted regions | Milestone 1: VHW TWG revived and meetings transpiring quarterly. (Note that through BIRCH, CHAI will provide support for biannual TWGs and will work with MOHCC to fund funding for additional ones.) Definition: Biannual TWGs conducted and actionable minutes shared with participants | BIRCH | 14146 |  | 2024-12-31 | 2024-12-31 | On track
Zimbabwe | LMH |  |  | BIRCH | 17511 |  | 2025-12-30 | 2025-12-30 | On track
Zimbabwe | LMH | Quarterly monitoring reports on implementation of community health investments (based on Detailed implementation plans) including identification of programmatic and absorption bottlenecks, problem solving and resolution in targeted regions | Milestone 2: Working with MOHCC and VHW partners, a template for quarterly monitoring reports will be developed, focused on monitoring BIRCH activitities, such as the operational plans, systems maturity, coordination of VHW investments, etc. Through stakeholder consultation and analysis, progress will be evaluated and a report will be updated each quarter. Definition: Monitoring report template defined and quarterly monitoring reports submitted, with detailed updates on operational plan progress, and key recommendations on resolving bottlenecks (such as inadequate absorption, finalising planned activities, etc) | BIRCH | 12536 |  | 2024-10-30 | 2024-10-30 | On track
Zimbabwe | LMH |  |  | BIRCH | 23376 |  | 2025-12-30 | 2025-12-30 | On track
Zimbabwe | LMH | Review and revision of national scope of practice and training package for PHC workforce (including CHWs and their supervisors) | Milestone: MOHCC training plans revised in line with the planned village health worker scale up plan and community health worker master list Definition: Updated training implentation plan aligned with MOHCC VHW scale up plan and community health worker master list submitted | BIRCH | 13487 |  | 2024-12-31 | 2024-12-31 | On track
Zimbabwe | LMH | Targeted Quality of Care/Quality Improvement rolled out in priority areas of CHW investment | Milestone: Working with MOHCC and VHW partners, a costed QC/QI plan will be developed, which will inform quarterly monitoring activities. Definition: Costed QC/QI plan submitted, with proposed partners targeted to implement interventions | BIRCH | 20905 |  | 2025-03-30 | 2025-03-30 | On track
Chad | Jhpiego |  |  | BIRCH | 642860 |  | 2025-12-31 | 2025-12-31
Niger | CHAI |  |  | BIRCH | 499943 |  | 2025-12-31 | 2025-12-31
Guinea-Bissau | ICHESS |  |  | BIRCH | 0
Central African Republic | ICHESS |  |  | BIRCH | 142864
Chad | ICHESS |  |  | BIRCH | 412218
Congo | ICHESS |  |  | BIRCH | 416172
Madagascar | ICHESS |  |  | BIRCH | 409769
Mauritania | ICHESS |  |  | BIRCH | 435869
South Sudan | ICHESS |  |  | BIRCH | 412412
Niger | ICHESS |  |  | BIRCH
BIRCH HQ | ICHESS |  |  | BIRCH

## IC Ceilings
Country | IC Approved Ceiling
Africa CDC | 916666.67
BIRCH HQ | 3377263.65
Burkina Faso | 250000
Cameroon | 300000
Central African Republic | 366666.67
Chad | 733333.33
Congo | 916666.67
Côte d'Ivoire | 250000
Ethiopia | 366666.67
Ghana | 750000
Guinea | 916666.67
Guinea-Bissau | 300000
JHPIEGO HQ | 275000
Liberia | 916666.67
Madagascar | 750000
Malawi | 916666.67
Mali | 916666.67
Mauritania | 916666.67
Niger | 916666.67
Nigeria | 916666.66
Sierra Leone | 500000
South Sudan | 300000
Tanzania | 750000
Uganda | 300000
Zambia | 500000
Zimbabwe | 300000

## Invoices
Purchase Order/Country | Partner | Associated PO | Pre-payment Amount | BIRCH Amount | SI Amount | Total PO Amount | Invoice Name | Invoice Period | Invoice Date | Narrative Report Drafted | Invoice Drafted | Invoice uploaded to isupplier | Date of remittance from GF
Africa CDC | FAH | 2024-005199 | 133544 | 517459 | 0 | 517459 | FAH-ACDC 01 P | Prepayment | 2024-07-27 | N/A | FAH-ACDC 01 P | 2024-08-23 | 2024-09-18
Burkina Faso | Living Goods | 2024-005339 | 77389 | 223226 | 218868 | 442094 | LGBIR-BFA 01 | Prepayment | 2024-07-18 | N/A | LGBIR-BFA 01 | 2024-07-23 | 2024-09-11
Cameroon | CHAI | 2024-005599 | 81225 | 300000 |  | 300000 | CHBIR-CAM 01 P | Prepayment | 2024-08-12 | N/A | CHBIR-CAM 01 P | 2024-08-15 | 2024-09-11
Cote d'Ivoire | Muso | 2024-005594 | 178105 | 729010 | 623290 | 1352300 | MUSBIR2-CIV 01 P | Prepayment | 2024-08-14 | N/A | MUSBIR2-CIV 01 P | 2024-08-15 | 2024-09-11
Ethiopia | LMH | 2024-005343 | 143064 | 191086 | 213518 | 404604 | BIRET2- 01 | Prepayment | 2024-07-18 | N/A | BIRET2- 01 | 2024-07-23 | 2024-09-03
Ghana | CHAI | 2024-005600 | 190427 | 750000 |  | 750000 | CHBIR-GHA 01 P | Prepayment | 2024-08-12 | N/A | CHBIR-GHA 01 P | 2024-08-15 | 2024-09-11
Guinea | Integrate | 2024-005334 | 216038 | 437303 | 0 | 437303 | GUIBIR-INT 01 P | Prepayment | 2024-07-22 | N/A | GUIBIR-INT 01 P | 2024-07-23 | 2024-09-03
BIRCH HQ | LMH | 2023-008064 | 926858 | 1899153 |  | 1899153 | BIRCH HQ2 | Prepayment | 2024-07-17 | N/A | BIRCH HQ2 | 2024-07-23 | 2024-09-03
Kenya | FAH | 2024-005598 | 22545 | 0 | 225454 | 225454 | FAHSI-KEN 01 P | Prepayment | 2024-08-07 | N/A | FAHSI-KEN 01 P | 2024-08-15 | 2024-09-11
Liberia | LMH | 2024-005340 | 123543 | 413657 | 226303 | 639960 | BIRLI2- 01 P | Prepayment | 2024-07-18 | N/A | BIRLI2- 01 P | 2024-08-23 | 2024-09-18
Malawi |  | 2024-005200 | 146113 | 405610 | 0 | 405610 | BIRMA2- 01 P | Prepayment | 2024-08-12 | N/A | BIRMA2- 01 P | 2024-08-15 | 2024-09-11
Mali | Muso | 2024-005597 | 308706 | 914792 | 496570 | 1411362 | MUSBIR2-MALI 01 P | Prepayment | 2024-08-14 | N/A | MUSBIR2-MALI 01 P | 2024-09-18
Nigeria
Senegal | FAH | 2024-005337 | 25070 | 0 | 250699 | 250699 | FAHSI-SEN 01 P | Prepayment | 2024-07-18 | N/A | FAHSI-SEN 01 P | 2024-07-23 | 2024-08-28
Sierra Leone | LMH | 2024-005338 | 75153 | 505960 | 0 | 505960 | BIRSL2- 01 P | Prepayment | 2024-07-18 | N/A | BIRSL2- 01 P | 2024-07-23 | 2024-08-20
Tanzania
Uganda | Living Goods | 2024-005595 | 144822 | 298571 | 0 | 298571 | LGBIR-UGA 01 P | Prepayment | 2024-08-07 | N/A | LGBIR-UGA 01 P | 2024-08-15 | 2024-09-11
Zambia | FAH | 2024-005201 | 144337 | 293487 | 253609 | 547096 | FAHBIR2-ZAM 01 P | Prepayment | 2024-07-18 | N/A | FAHBIR2-ZAM 01 P | 2024-07-23 | 2024-09-03
Zimbabwe | CHAI | 2024-005856 | 141811 | 300000 |  | 300000 | CHBIR-ZIM 01 P | Prepayment | 2024-08-27 | N/A | CHBIR-ZIM 01 P | 2024-08-28 | 2024-09-25

## POs
Country | Partner | BIRCH Focal Person | BIRCH Funding (2024) | SI Funding (2024) | Workplan and Budget | Workplan and Budget .xlsx | SEAH | Due Diligence/Partner Review | POs drafted | PO Signed | Subcontracting Status
Africa CDC | FAH | BMutua@financingalliance.org | Yes | No | ACDC | Updated 240611 ACDC | N/A |  | ACDC | 19-Jul-2024-Signed | Complete
Burkina Faso | Living Goods | ndesire@financingalliance.org | No | Yes | BFA | 240701 BFA - BIRCH Workplan for Purchase Order - Please do not edit or revise this copy directly.xlsx | Complete |  | BFA | 17-Jul-2024-Signed | Complete
Cameroon | CHAI | BMutua@financingalliance.org | Yes | No | CMR | 240718 CMR - BIRCH Workplan for Purchase Order - Please do not edit or revise this copy directly.xlsx | Complete | Yes | CMR | 08-Aug-2024-Signed | Complete
Cote d'Ivoire | Muso | ndesire@financingalliance.org | No | Yes | CIV | 240719 CIV - BIRCH Workplan for Purchase Order - Please do not edit or revise this copy directly.xlsx | Complete |  | CIV | 14-Aug-2024-Signed | Complete
Ethiopia | LMH | rmukendi@financingalliance.org | Yes | Yes | ETH | 240611 ETH | Complete | N/A | ETH | 17-Jul-2024-Signed | Complete
Ghana | CHAI | BMutua@financingalliance.org | Yes | No | GHA | 240722 GHA - BIRCH Workplan for Purchase Order - Please do not edit or revise this copy directly.xlsx | Complete | Yes | GHA | 08-Aug-2024-Signed | Complete
Guinea | Integrate | ndesire@financingalliance.org | Yes | No | GIN | 240704 GIN - BIRCH Workplan for Purchase Order - Please do not edit or revise this copy directly.xlsx | Complete |  | GIN | 19-Jul-2024-Signed | Complete
BIRCH HQ | LMH | Pearl Aku Badu | Yes | No | HQ | 240611 HQ | N/A | N/A | HQ | 15-Jul-2024- Signed | N/A
Kenya | FAH | cnjuguna@financingalliance.org | No | Yes | KEN | 240718 KEN - BIRCH Workplan for Purchase Order - Please do not edit or revise this copy directly.xlsx |  |  | KEN | 06-Aug-2024-Signed | Complete
Liberia | LMH | cnjuguna@financingalliance.org | Yes | Yes | LBR | 240611 LBR | Complete | N/A | LBR | 17-Jul-2024-Signed | Complete
Malawi | LMH | rmukendi@financingalliance.org | Yes | No | MWI | 240619 MWI - BIRCH Workplan for Purchase Order - Please do not edit or revise this copy directly.xlsx | Complete | N/A | MWI | 30-Jul-2024-Signed | Complete
Mali | Muso | ndesire@financingalliance.org | Yes | Yes | MLI | 240719 MLI - BIRCH Workplan for Purchase Order - Please do not edit or revise this copy directly.xlsx |  |  | MLI | 14-Aug-2024-Signed | Complete
Nigeria | CHAI | BMutua@financingalliance.org | Yes | No | NGA (in progress) |  |  | Yes |  |  | Complete
Senegal | FAH | ndesire@financingalliance.org | No | Yes | SEN | 240704 SEN - BIRCH Workplan for Purchase Order - Please do not edit or revise this copy directly.xlsx |  |  | SEN | 17-Jul-2024-Signed | Complete
Sierra Leone | LMH | rmukendi@financingalliance.org | No | No | SLE | 240703 SLE - BIRCH Workplan for Purchase Order - Please do not edit or revise this copy directly.xlsx | Complete | N/A | SLE | 17-Jul-2024-Signed | Complete
Tanzania | BMF | BMutua@financingalliance.org | Yes | No | TZA | [5 empty] | Delayed
Uganda | Living Goods | cnjuguna@financingalliance.org | Yes | No | UGA | 240718 UGA - BIRCH Workplan for Purchase Order - Please do not edit or revise this copy directly.xlsx |  |  | UGA | 06-Aug-2024-Signed | Complete
Zambia | FAH | rmukendi@financingalliance.org | No | Yes | ZMB | 240619 ZMB - BIRCH Workplan for Purchase Order - Please do not edit or revise this copy directly.xlsx | Complete |  | ZMB | 16-Jul-2024-Signed | Complete
Zimbabwe | CHAI | BMutua@financingalliance.org | Yes | No | ZWE | 240731 ZWE - BIRCH Workplan for Purchase Order - Please do not edit or revise this copy directly.xlsx | Complete | Yes | ZWE | 27-Aug-2024-Signed | Complete